335 Points

1.	Historical information is the best input for the initiation phase

2.	Operations: are ongoing and repetitive

3.	Getting coffee from Wife is a Project, Getting Coffee from Vending Machine is OPERATION (There are no surprises!..Thanks ARI)

4.	The Resource Breakdown Structure shows various resources, both human and mechanical needed for project.

5.	Acquisition: When the performing organization lacks the in house staff needed to complete the project, the required services can be acquired from outside sources.

6.	Let the people involved in the conflict work it out first

7.	The best use of "collect project records" is to recall what happened on the project, good or bad.

8.	Planning phase is LEAST Risky

9.	Control Management System tracks the changes(not configuration management)

10.	Templates and forms which are available in the organization are reusable components. Any resource that can be reused as a useful tool is part of the total methodology of project planning

11.	Comparing proposals received from sellers done in the Conduct Procurements.

12.	Make payment to seller is done in the Administer Procurements

13.	Engineering is primarily responsible for creating design and test specifications.

14.	Control charts are graphic display of the results over a time of a process. They are used to determine if the process is "in control".

15.	Pareto chart: Focus on critical issues to improve quality

16.	Fishbone diagram/Ishikawa: Determines how various factors linked to potential problems or effects, root cause

17.	Control chart: Determines whether or not process is stable and within set limits .

18.	Histogram: ordered by frequency of occurrence, that shows how many results were generated by type or category of identified cause.

19.	Planning meetings are used to create the Risk Management plan.

20.	Approximating number of work periods required to complete individual activities with estimated resources is done in Estimate Activity Duration process.

Activity List ,Activity resource requirements and Resource Calendars are inputs of Estimate Activity Duration process. PMBOK Page no 177

21.	Monte Carlo Analysis: A schedule risk assessment technique that performs a project simulation many times in order to calculate a distribution of likely results

22.	The project team, led by the project manager, must write the quality policy for each project.

23.	For an immediate work, a letter contract may be sufficient

24.	Performance Measures are done in contract Administration

25.	Product Verification, Procurement Audit and creation of a contract file are done in CONTRACT CLOSURE

26.	Last step in Administrative closure is Release resources

27.	Employee records should be updated by PM when he completes the tasks assigned to him

28.	Individual development is the Foundation of Team development

29.	T&M – has the characteristics of both Fixed and Cost reimbursement

30.	Procurement Audit is the only tool and Technique of contract closeout process

31.	Procurement Audit is used to identify successes to transfer the success to other procurements

32.	Symbols are always used in the communications

33.	Independent estimates are prepared to compare  the cost  to an estimate created with

34.	Communication Management plan defines the  contents of the performance reports

35.	Team development with WEAK Matrix is very difficult

36.	Product of the Project is Actually created in EXECUTION Phase /Group

37.	Any change in the Project Charter needs to be approved by the SENIOR MANAGEMENT

38.	REFERRENT power= PM’s PERSONALITY POWER

39.	Work Authorization system Ensures that work is done at RIGH T TIME and in proper sequence

40.	Solicitation is the process of obtaining quotations , bids , offer,

41.	The cost expanded at the  completion  of phase is known as SINK costs

42.	Conflicting priorities in resource assignments – is an issue in the Matrix structure

43.	Monte carlo simulation provides PROBABILITY OF ANY TASK BEING AT THE CRITICAL PATH

44.	Scope verification should be done – WHEN A PROJECT IS TERMINATED to determine the extent of the completion

45.	Jurans Quality Triology = PLANNING IMPROVEMENT CONTROL

46.	UCL : Upper control limit : Is derived from Random variation

47.	UTL : Upper tolerance limit is the higher of two tolerance limits

48.	When original estimates are flawed  then EAC = AC + ETC

49.	Functional – FM has more power

50.	Projectized – PM has more power

51.	Balanced – PM and FM has equal power

52.	WEAK – FM has more power

53.	Strong – MATRIX – PM has more power

54.	BUYER provides the SoW

55.	MAKE or BUY is used for PLAN Purchases and Acquisitions

56.	Residual risks are REMINING RISKS

57.	Crashing is applying more resources to shorten the duration

58.	Risk mitigation is to DECREASE THE PROBABILITY OF RISK

59.	ELAPSED TIME is the time inclusive of NON working days

60.	Outsourcing IS RISK TRANSFERENCE

61.	Networks (diagram) identify the Activity  dependencies and  path convergence risks

62.	If IRR Is given the DO THE PROJECT SELECTION ONLY BASED ON THAT

63.	Sensitivity chart displays sensitivities in DESENDING ORDER

64.	Payment bonds are specifically designed to ensure that the prime contractor provides payment of Subcontractors, laborers, and sellers of material

65.	Quality is the process of completing the scope to meet stated or implied needs.

66.	CRASHING =MORE COST

67.	FAST TRACK =MORE RISK

68.	Monte Carlo analysis gives you:An indication of the risk involved in the project

69.	85% cost of quality = DEMING

70.	A process goes out of control when there are special causes of variation

71.	Worker needs to be involved in Management Practice = OUCHI’s THEORY Z

72.	Definite cost are most accurate

73.	Sensitivity Analysis are part of Quantitative Analysis

74.	Milestone Duration is ZERO

75.	PERT Is also a NETWORK DIAGRAM

76.	A statistical method that helps identify which factors may influence specific variables of a product or process under development or in production is DESIGN OF EXPERIMENTS

77.	Complex project will best fit in MATRIX org structure

78.	Pert is Superior to CPM

79.	BRUCE TRUKMAN Model is related to TEAMMANAGEMENT

80.	Payback period ended means Cumulative Revenue and cumulative cost from Starnet became equal

81.	Beta Distribution and Triangular distribution are probability distributions

used in Risk Analysis

82.	The project management team should have a working knowledge of statistical quality control, especially sampling and probability, to help evaluate quality control outputs.

83.	The area consisting of typically three standard deviations on either side of a mean value of a control chart to plot measured values found in statistical quality control – THIS IS DEFINITION FOR CONTROL CHARTS

84.	large number of simultaneously performed projects utilize the same groups of human and other resources – is called RESOURCE POOLING

85.	The inherent discount rate or investment yield rate produced by the project over a pre-defined period of time. = IRR

86.	PMBOK Guide process groups Interact based on DEMING SHEWARTS PLAN DO CHECK ACT cycle

87.	The critical chain Method modifies the  SCHEDULE to account for LIMITED RESOURCES

88.	SCOPE CREEP = UNMANAGED changes to the Project SCOPE

89.	Code of Ethics of PMI = RRFH Responsibility, respect, Fairness, honesty

90.	A group of related scheduled activities – shown as single aggregate activity for the reporting purpose is known as HAMMOCK Activity

91.	Cost base line does not include management reserve

92.	Stake holder model – SALIANCE GRID

93.	As per HERZBERG base Salary is a HYGINE FACTOR

94.	RANK THE IDEAS in BRAINSTOMING – NOMINAL GROUP

95.	Arbitration and mediation are Negotiation Techniques

96.	Standards are OPTIONAL , Regulations are REQUIRED

97.	What is the name and ethical code for adhering PMP = PMI code of ethics and professional conduct

98.	Single source seller means – there is only one seller the company wants to do business with

99.	Cost Performance baseline is represented as S curve

100.	Inspections are NOT called as Assessments

101.	Inspections are called as reviews, Audits and walkthroughs

102.	First time feedback to a team member = Informal verbal (Face 2 Face), second time FORMAL written

103.	Non verbal communication is about 55%

104.	Last stage of project closure is project Archives

105.	CPI is considered most critical EVM Metric

106.	Contract closure occurs before Administrative closure

107.	Resource leveling results in INCREASED PROJECT DURATION

108.	Administrative closure should be carried out at the completion of each phase of the project

109.	Measuring Quality of the product against standard is called Benchmarking

110.	Fait accompli – done deal/ non negotiable

111.	The nodes on the AOA diagrams represent completion of the activities and have ZERO time usage

112.	Straight line depreciation formula= (Initial cost-scrap value)/life

113.	Preparing the Financial plan requires both project Management and Industry specific Skills

114.	Statistical sampling for Inspection is used to reduce the cost of Quality control

115.	One method to determine how well the project is getting executed is using – CPI (Cost performance Index)

116.	Seller completes the work as specified, but the buyer is not happy – then the contract is said to be COMPLETE (not closed though)

117.	TCPI is the projection of the cost performance that must be achieved on the remaining work

118.	The objective of lesions learned document is continuous Improvement

119.	Training for the team members is not a prerequisite – it can happen during the project also

120.	Over allotted – then do resource leveling

121.	Withdrawal – has cooling off period – but the problem is not solved

122.	The most Important criteria for project selection is REALISM

123.	INFLATION – is a EXTERNAL UN Predictable RISK

124.	Team building is difficult in Matrix Org structure

125.	RDU = Remaining Duration

126.	The Pillars of the quality are DOING It RIGHT – first time and ZERO Defects

127.	Project risk is categorized by 3 factors a) Risk event, b) risk probability) amount at stake

128.	Probing, scratching and small bites  – are the behaviors of the contract negotiations

129.	The project scope management plan – will not have the project constraints and assumptions (RD, Scope statement and scope BSL – will)

130.	If you have to look/refer any plan – to respond regarding improving customer satisfaction – you need to look at QUALITY PLAN

131.	Lag means – make sure one tasks waits before it gets started

132.	Lead means you let the task get started before its predecessor is done

133.	Output for source selection is contract

134.	Participative leadership is most preferred leadership style

135.	Gert is a System Dynamics model

136.	Trigger is a warning sign

137.	People exhibit slowest rate of change (Bruce willis -16 BLOCKS)

138.	Sponsor does not create project charter

139.	Philip corsby – said QUALITY IS FREE

140.	An Expressed Warranty is a statement of characteristics of the product

141.	Which questions the functional manager is most likely to ask : WHO WILL DO THE TASK

142.	An activity that consumes no time or resources and shows only a dependency = DUMMY Activity

143.	The practice of ceasing mass inspections and ending awards based on price is credited to DEMING

144.	Making a GIANT leap followed by a period of Maturity = INNOVATION

145.	12 to 20% of the sales is estimated to be the cost of NON QUALITY

146.	To assimilate through the mind or senses is the process of UNDERSTANDING

147.	RISK response of eliminating a threat = RISK AVOIDANCE

148.	The stage of the negotiation meeting – when he points of concession is identified = scratch bargaining

149.	Completion of PROJECT scope is measured against the plan (not PRODUCT SCOPE)

150.	Performance specifications are measureable

151.	Quality control measurements are used to reevaluate and analyze the quality standards and processes and are fed back through: Quality ASSURANCE

152.	The final cost of the project is HIGH at the start and gets progressively LOW as the project continues

153.	On large or mega projects the integration is the responsibility of the project office

154.	If the results fall under customer tolerance then the results are acceptable to client

155.	Benchmarking is a Technique used in QUALITY PLANNING

156.	Lessons learned are professional obligation of the project Manager

157.	The project manager's ability to influence others whose cooperation and support are crucial to the project is called: DE FACTO AUTHORITY

158.	Taguci loss function states that - VARIATION from Target Value Increases, the Loss also INCREASES

159.	Contract is LEGAL relationship and project is not

160.	Withdrawal is the LEAST preferred method by PM’s

161.	Risk audit documents the effectiveness of the risk responses

162.	Triangular distribution = PERT – Relies on Optimistic, Pessimistic and Most likely estimates(in Risk rating)

163.	Brain storming and Lateral Thinking are used in scope definition for ALTERNATIVES IDENTIFICATION

164.	Progressive Elaboration is what happens in rolling wave planning process

165.	Avoid, Mitigate, Transfer, Accept – are applicable for Negative Risks also

166.	Communications are COMPLEX in Matrix organization

167.	EVM does not play a major role in QUALITY MANAGEMENT PG

168.	Successor Activity LS- Duration of current activity= LS of Current Activity

169.	FIRM FIXED PRICE = Seller carries COST RISK, Buyer carries SCOPE RISK

170.	Releasing the resources from the project is what done as LAST ACTIVITY

171.	Procurement documents ensure the receipt of complete proposals

172.	Project Performance appraisal focus on How individual team member is performing in the team

173.	Baseline is established during the PLANNING

174.	Meetings are always classified as INFORMAL VERBAL

175.	BCR 1.8 means that revenue from the project is 1.8 times the cost

176.	Training the team member in GENERAL Skills is the function of the FUNCTIONAL MANAGER

177.	High Standard Deviation is High Risk.

178.	CPM - FLOAT usage; CCM - Buffer usage.

179.	Costs and staffing levels are lowest early in the life cycle, peak while the project work is underway, and then drop off as the project nears completion.

180.	Risk is highest early in the project since uncertainty is high about the project’s deliverables, resource needs, and work required.

181.	Stakeholder Influence in the project and its deliverables is highest early in the life cycle but diminishes as the project proceeds...

182.	Controlling unexpected project cost is to engage stakeholders early to prevent unnecessary and costly changes later in the project.

183.	The payback period tells us how long it will take to recoup the expense of the project, so a shorter payback period is better.

184.	BALANCED MATRIX: Folks who work in a balanced matrix organization report to a PM AND a functional manager equally.

185.	STRONG MATRIX: Project managers have more authority than functional managers, but the team still reports to both managers.

186.	Portfolio: A portfolio is a group of projects or programs that are linked together by a business goal.

187.	Program: A program is a group of projects that are closely linked, to the point where managing them together provides some benefit

188.	Project: A project is any work that produces a specific result and is temporary. Projects always have a beginning and an end. But they are never ongoing

189.	Portfolios are organized around business goals and Programs are organized around a shared benefit in managing them together."

190.	ROI = (Benefit – Cost)/Cost

191.	IRR is the discount rate when NPV equals zero.

192.	IRR assumes that cash inflows are reinvested at the IRR value.

193.	IRR:  You should choose projects with the highest IRR value.

194.	Mathematical models is that they use linear, dynamic, integer, nonlinear, and/or multi-objective programming in the form of algorithms—or in other words, a specific set of steps to solve a particular problem. Mathematical models are also known as Constrained optimization methods

195.	Benefit Measurement Methods: employ various forms of analysis and comparative approaches to make project decisions. These methods include comparative approaches such as cost-benefit analysis, scoring models, and benefit contribution methods that include various cash flow techniques and economic models.

196.	NET PRESENT VALUE - NPV: When you get a positive value for NPV, it means that the project will earn a return at least equal to or greater than the cost of capital.

197.	INTERNAL RATE OF RETURN - IRR: is the discount rate when the present value of the cash inflows EQUALS the original investment

198.	The primary difference between focus groups and facilitated workshops are that focus groups are gatherings of prequalified subject matter experts and stakeholders and facilitated workshops consist of cross-functional stakeholders who can define cross-functional requirements.

199.	Completion of Project Scope is measured against the Project Management Plan.

200.	Completion of Product scope is measured against Product Requirements.

201.	PMI advocates Project Objectives that follow the SMART guideline. S - Specific; M - Measurable; A - Assignable; R - Realistic; T - Timely.

202.	Control Account may include one or more Work Packages, each Work Package represents only one Control Account.

203.	The WBS doesn’t show the order of the work packages or any dependencies between them.

204.	Scope verification is primarily concerned with ACCEPTANCE of deliverables. Quality control is done before scope verification.

205.	Product scope: means the features and functions of the product or service that you and your team are building.

206.	Project scope: is all of the work that needs to be done to make the product.

207.	The work package is the LOWEST level on a WBS;

208.	The WBS doesn’t show the order of the work packages or any dependencies between them

209.	Verify Scope: The process of formalizing acceptance of the completed project deliverables. Usually performed after Perform Quality Control.

210.	Verify Scope happens at the end of each phase and the project and upon delivery of Product/Service/Result.

211.	Verify Scope is concerned with completeness and acceptance, and Perform Quality Control is concerned with correctness.

212.	If the project is cancelled/terminated before completion, Verify Scope is performed to show where the Project was in relation to the Scope when it ended.

213.	If we don't receive a final sign off from our customer; we have to escalate the issue to our Management.

214.	Defining activities is an iterative process performed together by the project manager and the project team member by further decomposing the WBS work packages

215.	ADM’s drawback is that it can only show finish-to-start (FS) relationships

216.	In order to show relationships between tasks on different node branches, ADM diagrams use dummy activities

217.	The Arrow Diagramming Method (ADM) creates diagrams known as activity-on-arrow (AOA).

218.	The Precedence Diagramming Method (PDM) creates diagrams known as activity-on-node (AON).

219.	Lead time causes the successor task to begin before its predecessor task concludes...for example FS-2 would schedule the successor task to start before the predecessor task finish.

220.	Lag time causes the successor task to begin some time after its predecessor task concludes...for example, FS+1 would delay the start of the successor by 1 day.

221.	Rough order of Estimate = +-50%

222.	Resource Calendars specify WHEN and HOW LONG identified project resource will be available during the project.

223.	Analogous is TOP DOWN

224.	Parametric is More Accurate

225.	Bottoms up is Accurate (When Parametric was not given)

226.	Duration is the amount of time that an activity takes, while effort is the total number of person-hours that are expended.

227.	Resource leveling can cause the original critical path to change.

228.	Path Convergence: The merging or joining parallel schedule network paths into the same node in a project schedule network diagram.

229.	Path convergence is characterized by a schedule activity with more than one predecessor activity.

230.	Path Divergence: Extending or generating parallel schedule network paths from the same node in a project schedule network diagram.

231.	Path divergence is characterized by a schedule activity with more than one successor activity.

232.	Sunk Costs: costs incurred that cannot be reversed irrespective to future events

233.	Value Engineering/ Analysis: finding less costly way to do the same work. E.g. outsourcing

234.	Marginal analysis: Spend time on improvement if it improves revenues or productivity.

235.	Order of Magnitude Estimate: Rough Order of Magnitude (ROM): -50% to +50% (at Initiation) as the project moves, estimates should become more accurate,

236.	Direct cost: include dedicated labor, material, supplies, equipment, licenses, fees, training, travel, or professional service fees - [Applied directly to THIS project]

237.	Indirect cost: Example, if a color printer is shared by several project teams, it’s difficult to definitively determine what percentage of costs each should share. [Expenses not for ONE project - these are Shared Expenses]

238.	Variable cost: fluctuate and can't be predicted with absolute certainty. For example, travel or transportation costs that can change depending upon the cost of fuel or  certain commodities and types of raw materials.

239.	Fixed cost: are static throughout the project or have only a small likelihood of fluctuation. Fixed costs are usually for items such as rents, leases, licenses, salaries, and fixed fees

240.	Life Cycle Costing includes Acquisition, Operation, Maintenance, and Disposal Costs

241.	The Scope Statement provides the Product Description, Acceptance Criteria, Key Deliverables, Project Boundaries, Assumptions, and Constraints about the Project.

242.	QUALITY: is defined as degree to which your project fulfills requirements. Customer satisfaction, Fitness for use, Conformance to requirements

243.	Cost benefit: Looking at how much your quality activities will cost.

244.	Benchmarking: means using the results of quality planning on other projects to set goals for your own.

245.	Design of experiments: is the list of all the kinds of tests you are going to run on your product.

246.	Attribute Sampling: is binary, it either conforms to quality or it doesn’t (YES or NO).

247.	Variable Sampling: Measures how well something conforms to quality (RANGES).

248.	Special Causes: considered unusual and preventable by process improvement.

249.	Common Causes are generally acceptable.

250.	Tolerances deal with the limits your project has set for product acceptance.

251.	Control Limits are set at three standard deviations above and below the mean. As long as your results fall within the control limits, your process is considered to be in control.

252.	Tolerances focus on whether the product is acceptable, while Control Limits focus on whether the process itself is acceptable. (Control limit is for PROCESS)

253.	Control Charts: The upper and lower control limits are set at THREE STANDARD DEVIATIONS ABOVE and BELOW MEAN.

254.	Rule of Seven: If seven or more consecutive data points fall on one side of the mean, they should be investigated. This is true even if the seven data points are within control limits.

255.	Just In Time (JIT): To reduce expensive cost of holding inventory, many companies decrease inventory close to zero. A company using JIT must have high quality practices.

256.	Cost of Quality = Prevention cost + Appraisal cost + control cost

257.	Low grade is OK, but Low Quality is NOT OK

258.	Quality assurance is focused on the processes and not the quality of the deliverables.

259.	This is important for us to remember: quality assurance is concerned with quality processes while quality control is concerned with quality deliverables.

260.	Flow Chart: Shows HOW PROCESSES INTERRELATE.

261.	Histogram (Column Chart): It shows HOW OFTEN something occurs, or its FREQUENCY (no Ranking).

262.	Pareto Charts (80-20 rule): This is a Histogram showing defects RANKED from GREATEST to LEAST. This rule states that 80% of the problems come from 20% of the causes. It is used to help determine the FEW ROOT CAUSES behind the MAJORITY OF THE PROBLEMS on a project.

263.	Run Chart: tell about TRENDS in the project. Shows the HISTORY and PATTERN.

264.	Scatter Diagram: It is powerful tool for SPOTTING TRENDS in Data. Scatter Diagrams are made using two variables (a dependent variable and an independent variable).

265.	W. Edwards Deming = Plan DO- check- Act + He also developed 14 activities for implementing quality

266.	Philip Crosby = ZEro Defects,

267.	Dr. Genichi Taguchi developed the concept of 'Loss Function'.

268.	KAIZEN = process Improvement

269.	special causes are considered preventable. For example, a backup generator failed to start up during a power failure. The failure of the backup generator can be prevented in the future through regular mechanical maintenance and operational tests.

270.	Common causes are thus generally considered as non-preventable and accepted as part of the process.

271.	Inspection keeps errors in the product from reaching the customer. Prevention keeps errors from occurring in the process.

272.	FORMAL, REWARD, PENALTY are powers derived from project managers position in the company.

273.	Theory X - Autoritarion leadership style

274.	Theory Y - Autoritarion Democratic/ Laissez- faire leadership style

275.	Theory Z - Autoritarion Democratic leadership style

276.	Laissez-faire: The leader turns nearly all control over to the group and is generally absent.

277.	In a matrixed organization, the project manager doesn’t have legitimate power, because the team doesn’t directly report to the project manager.

278.	Conflict can come from seven main sources, of which the first three account for 50% . They are 1. Schedules, 2. Priorities, 3. Manpower/human resource availability, 4. Technical opinions, 5. Procedural or project administration, 6. Costs,7. Personalities (SP is first 2 and CP is last 2)

279.	Generally, only one person is assigned Accountability for a work package, but more than one person may be responsible for performing the work on a work package

280.	Confronting: It’s a Win-Win situation

281.	Compromising: Lose-Lose method

282.	Withdrawal: Lose-Leave method

283.	Smoothing: Lose-Yield method

284.	Forcing: Win-Lose method (Worst way).

285.	Salience Model - describing classes of stakeholders based on their Power, Urgency and Legitimacy.

286.	SENDER'S responsibility to make the message clear, complete, and understood

287.	Nonverbal communication means your gestures, facial expressions, and physical appearance while you are communicating your message.

288.	Paralingual communication is the tone and pitch of your voice when you’re talking to people. If you sound anxious or upset, that will have an impact on the way people take the news you are giving

289.	Distribute Information is concerned with general project information, such as meeting minutes, issues, and correspondence.

290.	Report Performance focuses on performance reporting against baselines, such as scope, schedule, cost, or quality. Report Performance uses time, cost, and related work performance information.

291.	According to Kerzner - "90% of the Project Manager's time is spent communicating"

292.	Management Skills =  Presentations skills, negotiation skills, writing and public speaking skills.

293.	Risk Breakdown Structure (RBS): It is not breaking down the actial risks, instead, we are breaking down the CATEGORIES of risks that we will evaluate.

294.	The amount of tolerance a person or organization has for risks is referred to as its risk utility,

295.	Watchlist: Low priority risks should be regularly monitored so make sure they are not occurring and that their probability, impact, or priority hasn't changed.

296.	Risk Score: The probability and impact score for the risk. This is obtained from a formula (usually probability x impact) defined in the risk management plan and generated from the probability and impact matrix.

297.	The management reserve is for unknown-unknowns—things that you haven’t planned for but could impact your project.

298.	The contingency reserve is for known - unknowns, or risks that you know about and explicitly planned for and put in your risk register.

299.	Transfer: Transference assigns all or part of risk to a third party through outsourcing, contracts, insurance, warranties, guarantees, or performance clauses.

300.	Risk response- fails> then contingency plan...If contingency plan fails then > Fall back plan, i.e in other words=> It can be looked at as a contingency plan for the contingency plan

301.	CPFF - More risk for BUYER (some say T&M)

302.	FFP - More risk for SELLER

303.	UNILATERAL: this is a special class of contract in which the seller doesn't have to explicitly accept the offer in order for a contract to be established. This is a unilateral contract, and the best example is a purchase order (PO).

304.	Procurement closure needs to happen before Project Closure. All procurements MUST be CLOSED before the project is closed.

305.	Administrative closure is COMPLETE PROJECT Closure - so it can be done only once for project (or) Phase

306.	Claims are usually addressed through the contract change control system

307.	The payment system is how your company pays its sellers.

308.	100% rule comes in WBS

309.	Force Majeure Risks, such as Earthquakes, Floods, Acts of Terrorism, Etc., should be covered under Disaster Recovery Procedures instead of Risk Management.

310.	Journey to Abilene= Committee decisions can have the paradox outcome, that a jointly made or approved decision is not desired by any individual group member.(nobody likes the outcome)

311.	What is a constructive change? = consideration of undocumented change = A direction by the buyer or an action taken by the seller that the other party considers an undocumented change to the contract.

312.	Getting collective action from a group of people who may have quite different interests is 'Politics'.

313.	Arbitration is a form of negotiation. Technically, it is a form of assisted negotiation.

314.	Primary Responsibility of the Project Manager is 'Interact with others in a Professional Manner while completing the project'.

315.	GERT, Graphical Evaluation and Review Technique, allows for conditional advancement. GERT allows for branching and loopbacks.

316.	Subnets are often included in network templates to summarize common activities in a project.

317.	Parkinson's Law states that work will expand to fulfill the time allotted to it. (SUPER!- That’s what we do in real life right…)

318.	Soft logic allows the project manager to make decisions based on conditions outside of the project, best practices, or guidelines.

319.	Milestone Schedule can also be called as Master Schedule.

320.	The arrow diagramming method does not support finish-to-finish of relationships.

321.	GERT is the only diagramming technique that allows loops.

322.	The primary purpose of a network diagram is to show logical relationships.

323.	Value analysis is a way of finding the least expensive way to do the work.

324.	Fringe benefits are included in overhead and are part of indirect costs.

325.	QA is typically management process

326.	Q: Optimal quality is reached at what point? A: When revenue from improvement equals the incremental costs to achieve the quality. Marginal analysis provides that optimal quality is reached when the cost of the improvements equals the incremental costs to achieve the quality.

327.	Design of experiments uses experiments and 'what-if' scenarios to determine what variables are affecting quality.

328.	Having an allowable defect rate is an example of the cost of non-quality. Any system or process that will accept defects adds cost to the product or service.

329.	Staffing Management Plan: WHEN and HOW resource will be ADDED and TAKEN OFF the team.

330.	A corner office is a "perk" whereas health benefits are a fringe benefit.

331.	Mentoring: is the work that a project manager may be frequently called on to perform.

332.	Performance issues are senior and functional management's responsibility - usually the manager who supervises the resource.

333.	Conflict is not a filter of communication—it is a communication hindrance.

334.	Nonverbal communication carries 55 percent of the message you send. With this much at stake, nonverbal communication is of major importance.

335.	The utility function describes a person's willingness to tolerate risk.

336.	For immediate work, a letter contract may suffice. The intent of the letter contract is to allow the vendor to get to work immediately to solve the project problem.

337.	When you must begin work immediately without a procurement statement of work, the most appropriate choice is time and material.

338.	Outputs of all 42 Processes will be stored in PMIS.

339.	Cause & Effect/Ishikawa/Fishbone Diagram or 5 WHY Technique.

340.	The BIG Four: 1. Ishikawa; 2. Deming; 3. Juran; and 4. Crosby.

341.	Leads and lags are APPLIED as part of the Develop Schedule process, but then they are ADJUSTED in the process of Control Schedule.

342.	Zero Schedule Varience (SV) means the task is completed.

343.	The To-Complete-Performance-Index (TCPI) is: The cost performance index (CPI) required in the remainder of a project to meet financial goals.

344.	The S curve is the cost performance baseline. The cost performance baseline is used to track cost performance based on the original plan plus approved changes.

345.     	Requirement Traceability Matrix helps preventing gold plating

346.	Parametric Estimates may not scale

347.	For cost plus contract RFP is suitable

348.	NPV will help u to build most precise business case

349.	Standard deviation in a chart measures PRECISION

350.	Changing Management Approach based on the team members experience = SITUATIONAL  CONTINUUM

351.	PMIS resides in EEF (enterprise environmental factors)

352.	ARMA is a econometric method (Auto regressive moving average)

353.	LOI is not a legal document

354.	PM can not be a lead negotiator

355.	Work Authorization systems helps in preventing scope creep