## Integration
INTEGRATION
Sl# | Inputs | Tools & Techniques | Outputs
1 | Develop Project Charter: The process of developing a document that formally authorize a project or a phase and documenting initial requirements that satisfy the stakeholder's needs and expectations. The initiator's (sponsor) signature on the Charter authorizes the project. The approved Project Charter formally initiates the project. SOW: The essential elements of the SOW are 1. WHAT is to be done (Product Scope Description), 2. the business REASON for doing it (Business Need), and 3. HOW the project supports the organization's strategy (Strategic Plan). And it is a written description of the project's product, service, or result. PMI calls a SOW for external organizations 'a contract statement of work'. For Internal Projects, the Project Initiator or Sponsor provides. For External Projects, the Customer provides as part of a bid document. Project Selection Methods: 1- Benefit Measurement Methods: a. Economic Models, b. Scoring Models, c. Comparative Approach, d. Benefit Contribution, and e. Murder Board 2- Constrained Optimization Methods: a. Linear, b. Non-Linear, c. Dynamic, d. Integer, and e. Multi-objective algorithms 3. Additional Methods: 1. Benefit Cost Ratio (BCR), 2. Economic Value Add (EVA) - If a project does not make more moeny than those opportunity costs, it has not truly added economic value to the organization, 3. Internal Rate of Return (IRR) - Bigger is better, 4. Opportunity Cost - 'What is the cost of the other opportunities we missed by investing our money in this project?'. The Smaller the opportunity cost, the better. 4. Payback Period - a Shorter payback period is better than a longer one., 5. Present Value (PV) and Net Present Value (NPV): Bigger PV or NPV makes a project more attractive., 6. Return on Investment (ROI) - Bigger is better., and 7. Retun on Invested Capital (ROIC) = Net Income (after tax) from Project / Total Capital Invested in the Project.
INITIATING | 1. Project Statement of Work (SOW) | 1. Expert Judgment | 1. Project Charter (PC)
| 2. Business Case (is the document that justifies why the project should be accomplished) | a. Project Charter is created based on some need, and it should explain that need. | e. PC should include a high-level milestone view of the project schedule.
| 3. Contract | b. PC is signed by the performing organization's Senior Management. | f. PC is a high-level document that does not include project details; the specifics of project activities
| 4. Enterprise Environmental Factors | c. PC names the PM and gives PM authority to manage. | will be developed later.
| 5. Organizational Process Assets | d. PC should include the high-level proj requirements, high-level Project Description, high-level Risks. | g. PC includes a summary-level prelim project budget. h. Show organizational, environmental and external CONSTRAINTS and ASSUMPTIONS.
2 | Develop Project Management Plan: The process of documenting the actions necessary to define, prepare, integrate, and coordinate all subsidiary plans. The Project Plan is "a formal, approved document that defines HOW the project is executed, monitored and controlled, and closed. It may be summary or detailed and may be composed of one or more subsidiary management plans and other planning documents". It would be approved by * The Project Manager, * The Project Sponsor, * The Functional Manager who are providing resources for the project. (for the exam we will do much better to think of the Project Management Plan as always being DETAILED).
PLANNING | 1. Project Charter | 1. Expert Judgment | 1. Project Management Plan
| 2. Outputs from Planning Processes |  | (The SCOPE mgmt plan, the SCHEDULE mgmt plan, the COST mgmt plan, the CHANGE mgmt plan, and the CONFIGURATION mgmt plan are created right here.)
3. Enterprise Environmental Factors
4. Organizational Process Assets
3 | Direct and Manage Project Execution: The process of perfoming the work defined in the project management plan to achieve the project's objectives. It occurs any time; we are following the project management plan to create project deliverables. Most of the project resources and costs are expended in this process. Change Requests: 1.Corrective Actions: Documented direction for executing the project work to bring expected future performance of the project work in line with the project management plan. 2.Preventive Actions: A documented direction to perform an activity that can reduce the probability of negative consequences associated with project risks. 3.Defect Repair: The formally documented identification of defect in the project componenet with a recommendation to either repair the defect or completely replace the component. 4.Updates: Changes to formally controlled documentation, plans, etc., to reflect modified or additional ideas or content. # Corrective and Preventive Actions do not normally effect the Project Baselines, only the performance against the baselines. # Any information (Schedule/Milestones/Cost/Quality/Etc) related to the deliverables being produced here could be considered Work Performance Information.
EXECUTING | 1. Project Management Plan | 1. Expert Judgment | 1. Deliverables
| 2. Approved Change Requests | 2. Project Management Information System - PMIS | 2. Work Performance Information
| 3. Enterprise Environmental Factors | (It can include both manual and automated systems | 3. Change Requests
| 4. Organizational Process Assets | used together, integrate, and disseminate the outputs of | 4. Project Management Plan Updates
|  | the Develop Project Management Plan Process) | 5. Project Document Updates
4 | Monitor and Control Project Work: The process of tracking, reviewing, and regulating the progress to meet the performance objectives defined in the project management plan. Any necessary changes in the work or the plan are identified and made int his process. # Mid-Project Evaluations are conducted while project work is still in progress. The main purpose of such evaluations is to determine if objectives are still relevant and if these objectives are being met. Lessons Learned should also be documented at this time instead of waiting for the project to be completed. A third party or people outside the team should be used to conduct mid-project evaluations.
M & C | 1. Project Management Plan | 1. Expert Judgment | 1. Change Requests
| 2. Performance Reports |  | 2. Project Management Plan Updates
| 3. Enterprise Environmental Factors |  | 3. Project Document Updates
4. Organizational Process Assets
5 | Perform Integrated Change Control: The process of reviewing all change requests, approving changes, and managing changes to 1. the deliverables, 2. organizational process assets, 3. project documents, and 4. the project management plan. It brings together (integrates) all of the other Monitoring and Controlling Processes. And it evaluate the IMPACT of a change across the entire project. Changes may be requested by any stakeholder involved with the project. # Perform Integrated Change Control is primarily focused on MANAGING CHANGE to the project's SCOPE, while Monitor and Control Project Work is primarily focused on MANAGING THE WAY that SCOPE is EXECUTED. # Approved Change Requests will be implemented by the Direct and Manage Project Execution process. # CCB is responsible for reviewing changes and change requests and its level of authority should be spelled out in the Project Management Plan.
M & C | 1. Project Management Plan | 1. Expert Judgment | 1. Change Request Status Updates
| 2. Work Performance Information | 2. Change Control Meetings | 2. Project Management Plan Updates
| 3. Change Requests |  | 3. Project Document Updates
4. Enterprise Environmental Factors
5. Organizational Process Assets
6 | Close Project or Phase: The process of finalizing all activities across all of the Project Management Process Groups to formally complete the project or phase. It is all about shutting the project down properly. This includes creating the necessary documentation and archives, capturing the lessons learned, ensuring that the contract is properly closed, and updating all organizational process assets. # The Transition implies that the product has been accepted and is ready for this handover.
CLOSING | 1. Project Management Plan | 1. Expert Judgment | 1. Final Product, Service, or Result Transition
| 2. Accepted Deliverables |  | 2. Organizational Process Assets Updates
3. Organizational Process Assets
# Project Charter's key aspects are: * Purpose and project objectives, * Project sponsor or authority, * Project description and requirements, * Success Criteria, * Acceptance Criteria, * Identified Risks, * Initial WBS, Preliminary Milestones and Summary Budget, and * Project Manager Assignment (with responsibility and authority level)
# Change Control System: It is also a collection of formal documented procedures that define HOW project change requests are submitted, validated, recorded, approved or rejected, communicated, and worked within the project. In many areas the Change Control System is a subset of the Configuration Management System.
# Configuration control is focused on the specification of both the deliverables and the processes while change control is focused on identifying, documenting and controlling changes to the project and the product baselines.

## Scope
SCOPE
Sl# | Inputs | Tools & Techniques | Outputs
7 | Collect Requirements: The process of defining and documenting stakeholders' needs to meet the project objectives. # TT1: Project Manager or Business Analyst will do the Interviews with Subject matter expert and it is One-to-one meeting # TT2: Focus Groups: (Brings together prequalified stakeholders and subject matter experts with trained Moderator) 1. Two-way focus group, 2. Dual moderator focus group, 3. Dueling moderator focus group, 4. Respondent moderator focus group, 5. Client participant focus group, 6. Mini focus group, 7. Teleconference focus group, and 8. Online Focus Group. # TT3: Facilitated Workshops: (Quick with skilled Facilitator and Key cross-functional stakeholders) Joint Application Development (JAD for SW Ind) and Quality Function Deployment (QFD for Production Ind). # TT4: Group Creativity Techniques: 1. Brainstorming, 2. Nominal Group Technique: where brainstormed ideas are voted upon and sorted by priority, 3. Delphi Technique, 4. Idea and Mind Mapping, and 5. Affinity Diagram: large numbers of ideas to be sorted into groups # TT5: Group Decision making techniques: • Unanimity: everyone agrees on single course of action, • Majority: support from more than 50% of the members of the group, • Plurality: the largest block in a group decides even if a majority is not achieved, • Dictatorship: one individual makes the decision for the group. # TT8: Types of Prototypes: 1.Proof-of-Principle Prototype, 2.Form Study Prototype, 3.Visual Prototype, and 4.Functional/Working Prototype. Modern Prototyping (Computerized) # Categories of Requirements: Project: 1. Business Requirements, 2. Project Mgmt Requirements, 3. Delivery Requirements, and 4. Political Requirements. Product: 1. Technical Requirements, 2. Security Requirements, 3. Performance Requirements, 4. Cost Requirements, and 5. Quality Requirements.
PLANNING | 1. Project Charter | 1. Interviews | 1. Requirements Documentation
| 2. Stakeholder Register | 2. Focus Groups | (WHAT needs to be performed and WHY each requirement is important on the project)
3. Facilitated Workshops
|  | 4. Group Creativity Techniques | 2. Requirements Management Plan (HOWs)
|  | 5. Group Decision Making Techniques | 3. Requirements Traceability Matrix
|  | 6. Questionnaires and Surveys | (Requirements and its source, WHO OWNS and the Status). Matrix depicts as Requirements (Rows) against Deliverables (Columns).
7. Observations ('Job Shadowing' by Obsorver)
8. Prototypes (providing a working model)
8 | Define Scope: The process of developing a detailed description of the Project and Product. It turns all requirements into a more detailed project scope statement. Project Scope statement includes: 1. Product scope description and Project goals, 2. Product acceptance criteria, 3. Project Deliverables, 4. Project inclusions and exclusions, 5. Project constraints and assumptions, and 6. Identified risks related to the scope. TT2: Product Analysis includes * Product Breakdown, * Systems Analysis, * Requirements Analysis, * Systems Engineering, * Value Engineering, and * Value Analysis. PMI advocates Project Objectives that follow the SMART guideline. S - Specific; M - Measurable; A - Assignable; R - Realistic; T - Timely.
PLANNING | 1. Project charter | 1. Product analysis | 1. Project Scope Statement
| 2. Requirements Documentation | 2. Alternatives Identification-Brainstorming are used most | 2. Project Document Updates
| 3. Organizational Process Assets | 3. Facilitated Workshops
4. Expert Judgment
9 | Create WBS: The process of subdividing project deliverables and project work into smaller, more manageable components. After creation; it becomes a HUB OF INFORMATION for the project. It is a primary tool for verifying and controlling the project's scope. Every level in WBS is the detailed explanation of the level above it. WBS is a graphical, hierachical chart, logically organized from top to bottom. # Code of account is used to name the WBS (Unique Identification), # Planning packages (Set of work) are between Control Accounts and Work Packages. # WBS isn’t time based, # WBS does form the Scope Baseline, # WBS is a communication tool, # Created by the entire Project Team WBS Dictionaly might include 1. the number of the node, 2. the name of the node, 3. the written requirements for the node, 4. to whom it is assigned, 5. time (Date Assigned and Date Due), 6. cost, and 7. accounting information. # Management Control Points (Control Account): Where the integration of scope, schedule, and cost take place and where performance is measured. Advantages: 1. EV Calculation take place, 2. It is the building block of Performance Measurement, and 3. The sum of the control accounts will add up to the total project value (Rule of thumb is 300 Hours). Control Account may include one or more Work Packages, each Work Package represents only one Control Account.
PLANNING | 1. Project Scope Statement | 1. Decomposition | 1. WBS
| 2. Requirements Documentation |  | 2. WBS Dictionary
| 3. Organizational Process Assets |  | 3. Scope Baseline (Scope Stmt + WBS + WBS Dict)
4. Project Document Updates
10 | Verify Scope: The process of formalizing acceptance of the completed project deliverables. Formal process to verify and obtain stakeholder acceptance of the completed project scope and deliverables. Usually performed after Perform Quality Control. # Verify Scope happens at the end of each phase and the project and upon delivery of Product/Service/Result. # Verify Scope is concerned with completeness and acceptance, and Perform Quality Control is concerned with correctness. # If the project is cancelled/terminated before completion, Verify Scope is performed to show where the Project was in relation to the Scope when it ended. # Verify Scope is all about comparing the Deliverables with the documented Scope to ensure that everything was completed. # Verify Scope is typically performed by the PM, the Sponsor, the Customer, and the Functional Managers, and the result is a formal, written acceptance by the appropriate stakeholders. # If we don't receive a final sign off from our customer; we have to escalate the issue to our Management. # Characteristics of Verify Scope: 1. Signoff, Review, Inspection, 2. Documenting completed deliverables, and 3. Ensuring that the deliverables conform to the requirements.
M & C | 1. Project Management Plan | 1. Inspection | 1. Accepted deliverables
| 2. Requirements Documentation | (It involves a point-by-point review of the Scope and the associated Deliverable). Examine the deliverables, Measure it, Inspect it, and Weigh it. | 2. Change Requests
| 3. Requirements Traceability Matrix |  | 3. Project Document Updates
4. Validated Deliverables
11 | Control Scope: The process of monitoring the status of the project and product scope and managing changes to the scope baseline. Scope Creep will be eliminated. Integrated Change Control spans: * Control Scope * Control Schedule * Control Cost * Quality Control * Monitor and Control Risk * Administer Procurements # Customer's interests should always be weighed heavily and disputes should be resolved in favor of the customer.
M & C | 1. Project Management Plan | 1. Variance analysis | 1. Work Performance Measurements
| 2. Work Performance Information | VA can be used to measure differences btwn what was defined in the Scope Baseline & what was created. It is useful in this process as a way to investigate and understand the root causes behind these differences. | 2. Change Requests
| 3. Requirements Documentation |  | 3. Project Management Plan Updates
| 4. Requirements Traceability Matrix |  | 4. Project Document Updates
| 5. Organizational Process Assets |  | 5. Organizational Process Assets Updates
# SCOPE MANAGEMENT is a presentation of logical processes to understand requirements, define, break down, and control the scope of the project, and verify that the project was completed correctly. The Project Manager should always be in control of scope through rigid management of the requirements, details, and processes, and scope changes should be handled in a structured, procedural, and controlled manner. Scope may refer to 1. Product Scope (Features and Functions), and 2. Project Scope (Work need to be completed).
# A Baseline (whether for Scope, Schedule, Cost, or Quality) is the Original Plan + All Approved Changes.
# Uncontrolled changes are often referred to as project scope creep. Scope Creep Results from * Poor initial requirements definition, * Failure to involve users in early stages, * A missing Scope Baseline, * Poor Change Control, * Projects take long therefore requirements also change, * Weak Management, and * Failure to manage user expectations.
# Work Performance Information: Information and data, on the status of the project schedule activities being performed to accomplish the project work, collected as part of the direct and manage project execution processes. # Task: Work not necessarily listed in the WBS and is the lowest level of effort on the project.
# Work Performance Measurements: Results from measurements when comparing PLANNED Vs ACTUAL Technical Performance.
# If a variance is a Beneficial Variance: * Keep that variance, * Issue a change request to update the Scope Baseline to do the changes in characteristics.

## Time
TIME
Sl# | Inputs | Tools & Techniques | Outputs
12 | Define Activities: The process of identifying the specific actions to be performed to produce the project deliverables. # Rolling wave planning: Let you plan as you go. # Planning Package (placeholder put between control accounts and work packages)
PLANNING | 1. Scope Baseline | 1. Decomposition | 1. Activity List
| 2. Enterprise Environmental Factors | 2. Rolling Wave Planning | 2. Activity Attributes
| 3. Organizational Process Assets | 3. Templates | 3. Milestone list
4. Expert Judgment
13 | Sequence Activities: The process of identifying and documenting relationships among the project activities. # Mandatory Predecessors (Hard logic), Discretionary Predecessors (Preferred logic, Soft logic), and External Predecessors.
PLANNING | 1. Activity List | 1. PDM (Precedence Diagramming Method) | 1. Project Schedule Network Diagrams
| 2. Activity Attributes | 2. Dependency Determination | 2. Project Document Updates
| 3. Milestone List | 3. Applying Leads and Lags
| 4. Project Scope Statement | 4. Schedule Network Templates
5. Organizational Process Assets
14 | Estimating Activity Resource: The process of estimating the type and quantities of material, people, equipment, or supplies required to perform each activity. # Resource Calendars specify WHEN and HOW LONG identified project resource will be available during the project.
PLANNING | 1. Activity list | 1. Alternatives Analysis | 1. Activity Resource Requirements
| 2. Activity Attributes | 2. Bottom-up Estimating | 2. Resource Breakdown Structure
| 3. Resource Calendars | 3. Published Estimating Data | 3. Project Document Updates
| 4. Enterprise Environmental Factors | 4. Project Management Software
| 5. Organizational Process Assets | 5. Expert Judgment
15 | Estimating Activity Duration: The process of approximating the number of work periods needed to complete individual activities with estimted resources. # Analogous (top down): is when you look at activities from previous similar activities. The degree of similarity affects accuracy. This technique should be used early in the estimating cycle when there is not much detail known about the activity. It uses Historical information and expert judgement. It is less costly, less time consuming than others, and less accurate. It can be applied to a total project or to segments of a project and may be used in conjunction with other estimating methods. # Parametric/Quantitately-Based Estimating: It uses a statistical relationsip between HISTORICAL DATA and OTHER VARIABLES (Ex: Square footage in construction) to calculate an estimate for activity parameters, such as cost, budget, and duration. It can be applied to a total project or to segments of a project and may be used in conjunction with other estimating methods. Cost = Qty in units X Unit Rate. # Three-Point Estimate or Triangular Distribution: Come up with three points, Optimistic, Pessimistic, and Most Likely (Realistic) = (P+R+O)/3 # PERT (Program Evaluation and Review Technique)/Beta/Weighted Three-Point Estimate = (P+4R+O)/6 # Standard Deviation σ = (P-O)/6 Effort: The number of labour units required to complete a schedule activity or WBS component. Usually expressed as staff hours, staff days, or staff weeks. (Requirements for effort estimation: The Expert Judgement, Task Complexity, Sill Level, and Expectations). Duration: The total number of work periods (not including holidays and non-working periods) required to complete a schedule activity or WBS component. Usually expressed as workdays or workweeks. (Requirements for Duration estimation: Resource Availability and Resource Capability). Elapsed Time: Waiting periods.
PLANNING | 1. Activity List | 1. Analogous Estimating | 1. Activity Duration Estimates
| 2. Activity Attributes | 2. Parametric Estimating | (It doesn't include LAGS. It may include some indication of the range of possible results.)
| 3. Activity Resource Requirements | 3. Three-point Estimates
| 4. Resource Calendars | 4. Reserve Analysis (As more precise information about the project becomes available, the contingency reserve may be Used, Reduced, or Eliminated). | 2. Project Document Updates
5. Project Scope Statement
6. Enterprise Environmental Factors
| 7. Organizational Process Assets | 5. Expert Judgment
16 | Develop Schedule: The process of analyzing activity sequences, durations, resource requirements, and schedule constraints to create the project schedule. It determines the planned start and finish dates for project activities and milestones. # Critical Path Method: It calculates the theoretical Early Start and Finish Dates, and Late Start and Finish Dates, for all activities without regard for any resource limitations, by performing a Forward and Backward pass analysis through the schedule network. Critical paths have either ZERO or NEGATIVE Total Float. # Critical Chain Method: The resource-constrained critical path is known as the Critical Chain. The longest sequence of resource-leveled tasks is the critical chain. It tries to adjust for problems in estimating and managing tasks that result from 1. poor multi-tasking, 2. estimates with too much contingency for uncertainty, 3. work that expands to fill the available time, 4. waiting until the latest possible time to start and 5. lack of prioritization. Critical Chain Method focuses on managing remaining buffer durations against the remaining durations of task chains. In CCM; buffers are two types: 1. Project Buffer (Protects the target finish date from slippage along the Critical Chain), and 2. Feed Buffer (Protects the Critical Chain from slippage along the Feeding Chains). # Float/Slak/Total Float: amount of time an activity can slip before it causes delay in project. * Float for activities on CP is 0. CP- next longest path= float. # LEAD: Task can be started before completion of the predecessor (Ex: Start writing the Training Material before completion of the Testing). # LAG: Finish to Finish - The successor cannot be started before finishing the predecessor (Ex: Pouring Concrete). # Schedule Compression: includes Fast-tracking and crashing. # Crashing almost always increases cost. Over Time is considered as Crashing. Cheapest Task has to be crashed first. # Heuristics: Rules for which no formula exists. Usually derived through trial and error. # Free Float: how much time an activity can be delayed without affecting the early start date of subsequent dependent activities. # Resource Leveling: can be used when shared or critical required resources are only available at certain times, are only available in limited quantities, or to keep resource usage at a constant level. It can often cause the original critical path to change.
PLANNING | 1. Activity List | 1. Critical Path Method | 1. Project Schedule (Formats 1. Milestone Charts, 2. Bar Charts, and 3. Project Schedule Network Diagrams)
| 2. Activity Attributes | 2. Critical Chain Method
| 3. Activity Resource Requirements | 3. Resource Leveling | 2. Schedule Baseline
| 4. Activity Duration Estimates | 4. What-if Scenario Analysis | 3. Schedule Data
| 5. Project Schedule Network Diagrams | 5. Applying Leads and Lags | 4. Project Document Updates
| 6. Resource Calendars | 6. Schedule Compression
| 7. Project Scope Statement | 7. Scheduling Tool
| 8. Enterprise Environmental Factors | 8. Schedule Network Analysis
9. Organizational Process Assets
17 | Control Schedule: The process of monitoring the status of the project to update project progress and managing changes to the schedule baseline. # Schedule Baseline is updated, whenever the Customer requests a significant change and when original estimates were wrong.
M & C | 1. Project Management Plan | 1. Performance Reviews | 1. Work Performance Measurements (SV & SPI values)
| 2. Project Schedule | 2. Variance Analysis (SV/SPI) | 2. Change Requests
| 3. Work Performance Information | 3. Resource Leveling | 3. Project Management Plan Updates
| 4. Organizational Process Assets | 4. What-if Scenario Analysis | 4. Project Document Updates
|  | 5. Adjusting Leads and Lags | 5. Organizational Process Assets Updates
6. Schedule Compression
7. Scheduling Tool
8. Project Management Software
# HAMMOCK Activity: For control and mangement communication, the broader, more comprehensive summary activity.
# Path Convergence: The merging or joining parallel schedule network paths into the same node in a project schedule network diagram. Path convergence is characterized by a schedule activity with more than one predecessor activity. # Path Divergence: Extending or generating parallel schedule network paths from the same node in a project shedule network diagram. Path devergence is characterized by a schedule activity with more than one successor activity.

## Cost
COST
Sl# | Inputs | Tools & Techniques | Outputs
18 | Estimate Costs: The process of developing an approximation of the monetary resources needed to complete project activities. It is performed after Define Scope, Create WBS, Define Activities, Estimate Activity Resources, and Estimate Activity Durations. # Cost of quality: Cost that is incurred to achieve required quality # Stranded/Sunk Costs: costs uncured that cannot be reversed irrespective to future events # Value Engineering/ Analysis: Doing the same work for less. E.g. outsourcing # Marginal analysis: Spend time on improvement if it improves revenues or productivity. # Order of Magnitude Estimate: Rough Order of Magnitude (ROM): -50% to +50% (at Initiation) as the project moves, estimates should become more accurate, Conceptual Est: -30% to + 50%, Preliminary Est: -20% to +30%, Definitive Est: -15% to +20%, Control Est: -10% to +15% (for Activities with relatively few unknowns).
PLANNING | 1. Scope Baseline | 1. Expert Judgment | 1. Activity Cost Estimates
| 2. Project Schedule | 2. Analogous Estimating (Gross Value Estmting apprch) | 2. Basis of Estimates
| 3. Human Resource Plan | 3. Parametric Estimating (Uses Statistical relationship) | 3. Project Document Updates
| 4. Risk Register | 4. Bottom-up Estimating
| 5. Enterprise Environmental Factors | 5. Three-Point Estimates
| 6. Organizational Process Assets | 6. Reserve Analysis
7. Cost of Quality
8. Vendor Bid Analysis
9. Project Management Estimating Software
19 | Determine Budget (Cost Performance Baseline): The process of aggregating the estimated costs of individual activities or work packages to establish an authorized cost baseline. Budget, is time-phased (WHAT costs will be incurred and WHEN they will be incurred). The Cost Baseline describes a detailed budget that shows costs and timelines for each work package or activity. It is performed after Define Activities, Estimate Activity Resources, Estimate Activity Durations, Develop Schedule and Estimate Costs. # Larger projects may be divided into multiple Cost Baselines.
PLANNING | 1. Activity Cost Estimates | 1. Cost Aggregation | 1. Cost Performance Baseline (S - curve)
| 2. Basis of Estimates | 2. Reserve Analysis | 2. Project Funding Requirements (Dotted Steps)
| 3. Scope Baseline | 3. Expert Judgment | (Expenditures, Liabilities, and Reserves)
| 4. Project Schedule | 4. Historical Relationships | 3. Project Document Updates
| 5. Resource Calendars | 5. Funding Limit Reconciliation
6. Contracts
7. Organizational Process Assets
20 | Control Costs: The process of monitoring the status of the project to update the project budget and managing changes to the cost baseline. -Cumulative CPI: The rate at which the project performance is meeting cost expectations from the beginning up to a point in time. Also used to forecast project’s cost at completion. CPIC (CPI Cumulative)= EVC (EV Cumulative)/ ACC (AC Cumulative) = Which calculates the project's performance up to a point in time. -To-Complete Performance Index (TCPI): performance needed in order to achieve earned value targets (either financial or schedule). Two forms, TCPIC and TCPIS. # TCPI (Based on BAC) = Work Remaining i.e, (BAC-EV) / Remaining Funds i.e., (BAC-AC) (lower than 1 is good) # TCPI (Based on EAC) = Work Remaining i.e, (BAC-EV) / Remaining Funds i.e., (EAC-AC) (lower than 1 is good) # TCPI calculation is based on a specified management goal. If the cumulative CPI falls below the baseline plan, all future work of the project will beed to immediately be performed in the range of the TCPI (BAC) to stay within the authorized BAC. Once management acknowledges that the BAC is no longer attainable, the PM will prepare a new EAC for the work, and one approved the project will work to the new EAC value and it supersedes the BAC. # The EVM method works well in conjunction with manual forecasts of the required EAC costs. The most common EAC forecasting approach is a MANUAL, BOTTOM-UP SUMMATION by the PM and Project Team. # Project Manager monitor EV, both incrementally to determine CURRENT STATUS and cumulatively to determine long-term PERFORMANCE TRENDS.
M & C | 1. Project Management Plan | 1. Earned Value Management (Variances and Trends) | 1. Work Performance Measurements
| 2. Project Funding Requirements | 2. Forecasting (EAC and ETC) | 2. Budget Forecasts
| 3. Work Performance Information | 3. To-complete Performance Index (TCPI) | 3. Change Requests
| 4. Organizational Process Assets | 4. Performance Reviews | 4. Project Management Plan Updates
|  | 5. Variance Analysis | 5. Organizational Process Assets Upd
|  | 6. Project Management Software | 6. Project Document Updates
# Project Cost Baseline = Project Estimates + (Cost) Contingency Reserves; # Project Cost Budget = Project Cost Baseline + Management Reserves
# PV: Planned Value / Budgeted Cost of Work Scheduled (BCWS) = BAC X Planned % Completed
# EV: Earned Value / Budgeted Cost of Work Performed (BCWP) = BAC X Actual % Completed
# AC: Actual Cost / Actual Cost of Work Performed (ACWP) = SUM of the Costs for a given period of time.
# Life Cycle Costing includes Acquisition, Operation, Maintenance, and Disposal Costs.
# The Cost Management Processes and their associated tools and techniques are usually selected during the project life cycle definition, and are documented in the Cost Management Plan (which has been produced by Develop Project Mgmt Plan Process). For example, the Cost Mgmt Plan can establish the following: 1. Level of Accurary (Rounding of the data), 2. Units of Measurement (Staff Hours, Staff Days, Weeks, or Lump Sum), 3. Organizational Procedures Links (The WBS component used for the Project Cost Accounting is called the Control Account (CA). Each Control Account is assigned a unique code or account number that links directly to the performing organization's Accounting System), 4. Contol Thresholds (Thresholds are typically expressed as percentage deviations from the baseline plan), 5. Rules of Performance Measurement (EVM rules of performance measurement are set), 5. Reporting Formats (Formats and frequency of various cost reports are defined), and 6. Process Descriptions (description of each of the three cost mgmt processes are documented).
# The Scope Statement provides the Product Description, Acceptance Criteria, Key Deliverables, Project Boundaries, Assumptions, and Constraints about the Project.
# Project Cost Control includes: 1) Influencing the factors that create changes to the authorized cost baseline, 2) Ensuring that all change requests are acted on in a timely manner, 3) Managing the actual changes when and ass they occur, 4) Ensuring that cost expenditures do not exceed the authorized funding, by period and in total for the project, 5) Monitoring cost performance to isolate and understand variances from the approved cost baseline, 6) Monitoring work performance against funds expended, 7) Preventing unapproved changes from being influded in the reported cost or resource usage, 8) Informing appropriate stakeholders of all approved changes and associated cost, and 9) Acting to bring expected cost overruns within acceptable limits.

## Quality
QUALITY
Sl# | Inputs | Tools & Techniques | Outputs
21 | Plan Quality: The process of identifying quality requirements and/or standards for the project and product, and documenting how the project will demonstrate compliance. Decisions made about quality can have a significant impact on other decisions such as scope, time, cost, and risk. Most Project Management Practitioners view SCOPE and QUALITY as INSEPARABLE. # If Quality Policy doesn't exist, the Project Team should write one for this project. "Determine WHAT the quality standards for the project will be and document HOW the project will be measured for compliance". # Cost benefit: Looking at how much your quality activities will cost. # Benchmarking: means using the results of quality planning on other projects to set goals for your own. # Design of experiments: is the list of all the kinds of tests you are going to run on your product. # Attribute Sampling :is binary, it either conforms to quality or it doesn’t (YES or NO). # Variable Sampling: Measures how well something conforms to quality (RANGES). # Special Causes: considered unusual and preventable by process improvement. # Common Causes are generally acceptable. # Tolerances deal with the limits your project has set for product acceptance. # Control Limits are set at three standard deviations above and below the mean. As long as your results fall within the control limits, your process is considered to be in control. ## Toleranes focus on whether the product is acceptable, while Control Limits focus on whether the process itself is acceptable. # Control Charts: The upper and lower control limits are set at THREE STANDARD DEVIATIONS ABOVE and BELOW MEAN. # Rule of Seven: If seven or more consecutive data points fall on one side of the mean, they should be investigated. This is true even if the seven data points are within control limits.
PLANNING | 1. Stakeholder Register | 1. Cost-Benefit Analysis | 1. Quality Management Plan
| 2. Scope Baseline | 2. Cost of Quality | 2. Quality Metrics (Defines how Q will be measured)
| 3. Cost Performance Baseline | 3. Control Charts | 3. Quality Checklists
| 4. Schedule Baseline | 4. Flowcharting | 4. Process Improvement Plan
| 5. Risk Register | 4. Benchmarking | 5. Project Document Updates
| 6. Organizational Process Assets | 5. Design of Experiments (DOE)
| 7. Enterprise environmental factors | 6. Statistical Sampling
8. Proprietary Quality Management Methodologies
9. Additional Quality Planning Tools
22 | Perform Quality Assurance: The process of auditing the quality requirements and the results from quality control measurements to ensure appropriate quality standards and operational definitions are used. "Use the measurements to see if the quality standards will be MET; VALIDATE the standards". # Imp Point: Perform Quality Assurance is primarily concerned with overall PROCESS IMPROVEMENT. It is not about inspecting the product for quality or measuring defects. Instead, Performance Quality Assurance is focused on steadily improving the activities and processes undertaken to achieve quality. # Proactive steps taken by PM and the mgmt team to insure the quality standards are being help and monitored.
EXECUTING | 1. Project Management Plan (Q M Pl & Process Imp Pl) | 1. Quality Audits (Key Tool) | 1. Change Requests (for Procedural Changes)
| 2. Quality Metrics (Defines how Q will be measured) | 2. Process Analysis | 2. Project Management Plan Updates
| 3. Quality Control Measurements | 3. Plan Quality and Perform Quality Control Tools | 3. Project Document Updates
| 4. Work Performance Information | and Techniques | 4. Organizational Process Assets Updates
23 | Perform Quality Control: The process of monitoring and recording results of executing the quality activities to assess performance and recommend necessary changes. This process uses the tool of INSPECTION to make sure the results of the work are what they are supposed to be. Perform Quality Control is the process where each deliverable is INSPECTED, MEASURED, and TESTED. This process makes sure that everything produced meets quality standards. "Perform the MEASUREMENTS and COMPARE to specific quality standards; IDENTIFY ways of eliminating the problem in the future". # Cause and Effect Diagram (Ishikawa/Fishbone): Used to show how different factors relate together and might be tied to potential problems. It imporves quality by identifying quality problems and trying to UNCOVER THE UNDERLYING CAUSE. # Flow Chart: Shows HOW PROCESSES INTERRELATE. # Histogram (Column Chart): It shows HOW OFTEN something occurs, or its FREQUENCY (no Ranking). # Pareto Charts (80-20 rule): This is a Histogram showing defects RANKED from GREATEST to LEAST. This rule states that 80% of the problems come from 20% of the causes. It is used to help determine the FEW ROOT CAUSES behind the MAJORITY OF THE PROBLEMS on a project. # Run Chart: tell about TRENDS in the project. Shows the HISTORY and PATTERN. # Scatter Diagram: It is powerful tool for SPOTTING TRENDS in Data. Scatter Diagrams are made using two variables (a dependent variable and an independent variable). # Statistical Sampling: It is a powerful tool where a RANDOM sample is selected instead of measuring the entire population.
MONITORING & CONTROLLING | 1. Project Management Plan (Q M Plan) | 1. Cause and Effect Diagram (Ishikawa/Fishbone) | 1. Quality Control Measurements
| 2. Quality Metrics | 2. Control Charts | 2. Validated Changes
| 3. Quality Checklists | 3. Flowcharting | 3. Validate Deliverables
| 4. Deliverables | 4. Histogram | 4. Change Requests
| 5. Approved Change Requests | 5. Pareto Chart | 5. Project Management Plan Updates
| 6. Work Performance Measurements | 6. Run Chart | 6. Project Document Updates
| 7. Organizational Process Assets | 7. Scatter Diagram | 7. Organizational Process Assets Updates
8. Statistical Sampling
9. Inspection
10. Approved Change Requests Review
# Plan Quality, Perform Quality Assurane, and Perform Quality Control map closely to the Plan-Do-Check-Act cycle as described by W. Edwards Deming (He also developed 14 activities for implementing quality). # Philip Crosby, similar to Deming, he too developed 14 Steps to improving quality. # Joseph Juran: Fitness-for-use, Juran Trilogy (Quality of Design, Quality of Conformance, and Quality Characteristics), Juran Trilogy approach Plan-Improve-Control. # Dr. Genichi Taguchi developed the concept of 'Loss Function'.
# Investment in Quality is usually born by the Organization (not by the project). # Plan-Do-Check-Act has been defined by SHEWHARD and modified by DEMING in ASQ Handbook.
# Quality is "the degree to which a set of inherent characteristics fulfill requirements."
# Total Quality Management (TQM): Everyone in the company is responsible for quality and is able to make a difference in the ultimate quality of the product. TQM shifts the primary quality focus away from the product that is produced and looks instead at the underlying process of how it was produced.
# Continuous Improvement Process (CIP)/KAIZEN: A philosophy that stresses constant process improvement, in the form of small changes in products or services.
# Just-In-Time (JIT): A manufacturing method that brings inventory down to Zero (or near Zero) levels. It forces a focus on quality, since there is no excess inventory on hand to waste. # • 1σ = 68.25% • 2σ = 95.46% • 3σ = 99.73% • 6σ = 99.99966% # ISO 9000: Ensures Companies document what they do and do what they document. It may be an important component of Performance Quality Assurance, since it ensures that an organization follows their processes. # Mutually Exclusive: one choice excludes the other. # CMMI: Defines the essential elements of effective processes.
# Statistical Independence: When the outcomes of two processes are not linked together or dependent upon each other, they are statistically independent.
# Six Sigma: Six sigma quality strives to make the overwhelming majority of the bell curve fall within customer quality limits. Six sigma is a quality management philosophy that sets very high standards for quality, and that one sigman quality is the lowest quality level, allowing 317,500 defects per 1,000,000 outputs, three sigma quality is higher, allowing 2,700 defects per 1,000,000, and six sigma is the highest of these, allowing only 3.4 defects per 1,000,000. Pharmaceutical Industry, the Airline Industry, and Power Utilities typically strive for higher levels of quality than six sigma would specify in some areas of their operations.

## HR
HUMAN RESOURCE
Sl# | Inputs | Tools & Techniques | Outputs
24 | Develop Human Resource Plan: The process of identifying and documenting Project Rols, Responsibilities, and Required Skills, Reporting Relationships, and creating a Staff Management Plan. The HR Plan documents project Roles and Responsibilities, Porject Organization Charts, and the Staffing Management Plan including the Timetable for Staff Acquisition and Release. It may also include Identification of Training Needs, Team-Building Strategies, Plans for Recognition and Rewards Programs, Compliance Considerations, Safety Issues, and the Impact of the Staffing Management Plan on the Organization. TT1: Three Primary Formats are 1. Hierachical, 2. Matrix (RAM - Responsibility Asssignment Matrix, which displays work packages in the rows and roles in the columns - Popular Type is RACI chart - R-Responsible; A-Accountable; C-Consult; I-Inform. It is important when team consists of Internal and External Resources), and 3. Text (Job/Position Descriptions and Role-Responsibility-Authority Forms - This tool is prticularly useful in Recruiting). TT2: For understanding Organizations and Teams behavior. TT3: Networking is the process of communicating with others within your "Network" of contacts - By networking within the organization, PM can understand the political and Organizational Forces that will influence the project. HR Networking activities include Proactive Correspondance, Luncheon Meetings, Informal Conversations including Meeting and Events, Trade Conferences, and Symposia. It can be a useful technique at the beginning of a project. O1: Resource Histogram - shows the resource usage for a given period of time. It illustrates the number of hours a person, department, or entire project team will be needed each week or month over the course of the project.
PLANNING | 1. Activity Resource Requirement | 1. Organization Charts and Position Descriptions | 1. Human Resource Plan - It has three componenets a. Roles and Responsibilities, b. Organization Charts, and c. The Staffing Management Plan
| 2. Enterprise Environmental Factors | 2. Organizational Theory
| 3. Organizational Process Assets | 3. Networking
25 | Acquire Project Team: The process of confirming human resource availability and obtaining the team necessary to complete project assignments. TT1: Pre-Assignment: Occasionally specific resources will be Pre-Assigned to fill a role. This may occur before the Human Resource Plan has been creaated and even before the project formally begins. TT2: Negotiation: It is an important sill for PM to cultivate. TT3: Aquisition: It refers to looking outside the organization for resources when they cannot be provided by your organization. TT4: Virtual teams are when all team members don’t work in the same location.
EXECUTING | 1. Project Management Plan | 1. Pre-Assignment | 1. Project Staff Assignments
| 2. Enterprise Environmental Factors | 2. Negotiation (Key Technique of this process) | 2. Resource Calendars
| 3. Organizational Process Assets | 3. Acquisition | 3. Project Management Plan Updates
4. Virtual Teams
26 | Develop Project Team: The process of improving the competencies, team interaction, and the overall team environment to enhance project performance. "Project Management Skills, Leadership Styles, Power, Team Building and the Motivation of people are all concepts that fall into this process." Five kinds of powers: Reward power, Expert power, Referent power, Punishment power (Coercive), and legitimate power (Formal power) - Reward and Expert as the most effective forms of power and Punishment/Coercive as the least effective. Recognition and Reward (Theories of Motivation) - Win-win rewards as the best choices for team building. • Maslow’s hierarchy of needs - You can’t achieve higher needs until you’re satisfied with the lower ones. Lower needs - 1. Physiological, 2. Security, 3. Acceptance. Higher Needs - 4. Esteem, 5. Self-Actualization. • Herzberg’s Motivation-Hygiene Theory: Hygiene factors (Company Policy, Supervision, Good relationship with boss, working conditions, Paycheck, Personal life, Status, Security, and Relationship with co-workers) does not make someone satisfied, but their absence will make someone unsatisfied. Hygiene factors do not motivate by themselves. Motivation factors (Achievement, Recognition, Work, Responsibility, Advancement, and Growth) will motivate, but they will not work without the Hygiene factors in place. • Douglas McGregor’s Theory X and Theory Y: Theory X - Team members are Selfish, Unmotivated, Dislike work (constant supervision is required - 'authoritarian management' style). Theory Y - Naturally motivated to do good work (manager trusts team members - 'participative management' style). • Dr. William Ouchi’s Theory of – “Z Theory”: Productivity can be increased by how well the workers and management get along and trust each other. Japanese style of management • David McLelland’s Achievement Theory(Theory of three needs): says that people need Achievement (need of achievement - nAch: High Risk or Low Risk projects may not appeal to them), Power (need of power - nPow: Institutional (Social) Power and Personal Power. Individuals with a desire for Social Power are usually more effective team members), and Affiliation (need for affiliation (nAff): They seek to maintain good relationships and do well in customer-facing team positions) to be motivated • Victor Vroom’s Expectancy Theory: If workers believe their efforts are going to be successful and rewarded, they will tend to be highly motivated and productive. • Contingency Theory (Fred E. Fiedler): In stressful times, a task-oriented leader will be more effective, while in relatively calm times a relationship-oriented leader will function more effectively. • Hersey and Blanchard's Life Cycle Theory: Leadership style must change with the maturity of individual employees. The PM's style should move from Directing, to Coaching, to Supporting, Then to Delegating as the project moves through its life cycle.
EXECUTING | 1. Project Staff Assignments (will have list | 1. Training | 1. Team Performance Assessments
| of all team members) | 2. Team-building Activities | 2. Enterprise Environmental Factors Upd
| 2. Resource Calendars | 3. Ground Rules
| 3. Project Management Plan | 4. Co-location
5. Recognition and Rewards
6. Interpersonal Skills (Soft Skills)
27 | Manage Project Team: The process of tracking team member performance, providing feedback, resolving issues, and managing changes to enhance the project performance. Methods of Conflict Mgmt: • Problem solving (Confronting): It’s a Win-Win situation (Highly favoured way) • Compromising: Lose-Lose method • Withdrawal: Lose-Leave method (PMI does not favour this method) • Smoothing: Lose-Yield method (Doesn't produce a solution) • Forcing: Win-Lose method (Worst way). Leadership styles: • Autocratic/Authoritarian/Directing: Strong style. The PM seeks little or no information from the team, and is the sole decision maker. • Bureaucratic/Persuading/Consultative Autocratic: Input is received from selected team members, but the PM is still the sole decision maker. • Democratic/Participative/Consensus: Consults team for open discussion and information gathering; uses help from team to come up with a decision. • Lassiez-faire/Delegating/Free Reign/Shareholder: (Poor Leadership Style) Little or no information exchange takes place within the project group. Team has ultimate authority on final decision, hands-off attitude. • Transactional: Transactional leadership is really just a way of managing (mangement by exception) rather than a true leadership style as the focus on the short-term tasks. • Transformational: A person with this leadership style is a true leader who inspires his or her team constantly with a shared vision of the future.
EXECUTING | 1. Project Management Plan | 1. Observation and Conversation | 1. Change Requests
| 2. Project Staff Assignments | 2. Project Performance Appraisals | 2. Project Management Plan Updates
| 3. Team Performance Assessments | 3. Conflict Management | 3. Organizational Process Assets Updates
| 4. Performance Reports | 4. Issue Log | 4. Enterprise Environmental Factors Updates
| 5. Organizational Process Assets | 5. Interpersonal Skills
# Generally, only one person is assigned Accountability for a work package, but more than one person may be responsible for performing the work on a work package.
# Training Expenses should be paid for by the Performing Organization or the Functional Manager and not by the Customer or the Project.
# Ground Rules: Formal or informal rules that define the boundaries of behavior on the project. It is important that ground rules be defined and communicated to the team members. # Five Stages of Team Development are: 1. Forming, 2. Storming, 3. Norming, 4. Performing, and 5. Adjourning
# Constructive Team Roles: Initiators, Information Seekers, Information Givers, Encouragers, Clarifiers, Harmonizers, Summarizers, and Gate Keepers.
# Distructive Team Roles: Aggressors, Blockers, Withdrawers, Recognition Seekers, Topic Jumpers, Dominators, and Devil's Advocates.
# The greatest project conflict occurs between Project Managers and Functional Managers. Most conflict on a project is the result of disagreement over Schedule, Priorities, and Resource. # Deligation is completely opposit to Micromanagement (it is completely opposite to Deligation)
# PM's Style of Leadership over Project Timeline: i. Directing Leader, ii. Coaching Leader, iii. Facilitating Leader, and iv. Supporting Leader
# PMI views the process of managing conflict within the project team as initially being the responsibility of the project team memebers.
# Staffing Mgmt Plan include: 1.Staff acquisitions, 2.Resource calendars/histogram, 3.Staff release plan, 4.Training needs, 5.Recognition & Rewards, 6.Compliance, and 7.Safety.

## Comm
COMMUNICATIONS
Sl# | Inputs | Tools & Techniques | Outputs
28 | Identify Stakeholders: Identify all people or organizations impacted by the project and document their interests, involvement and impact on project success. Stakeholder Analysis Steps: 1. Identify Stakeholders 2. Analyze & Classify Stakeholders 3. Develop Strategy. Stakeholders Classification Models: 1. Power/Interest Grid (Authority/Concern) 2. Power/Influence Grid (Authority/Involvement) 3. Influence/Impact Grid (Influence/Ability to effect Planning & Execution) 4. Salience Model - describing classes of stakeholders based on their Power, Urgency and Legitimacy. Categories: 1. Champions - Positive Attitude, 2. Neutral - No influence expected, 3. Challenger - Questions the project, 4. Decision Makers - Manage Challengers, Support Champions. Strategies: For Individuals - A. Assessment Matrix, B. Strategy Matrix. For Groups - A. Commmunication Strategy Matrix.
INITIATING | 1. Project Charter | 1. Stakeholder Analysis | 1. Stakeholder Register
| 2. Procurement Documents | (Participation Analysis) | 2. Stakeholder Management Strategy
| 3. Enterprise Environmental Factors | 2. Expert Judgment | (Stakeholder Analysis Matrix)
4. Organizational Process Assets
29 | Plan Communications: Determining the project stakeholder information needs and defining a communication approach. * Plan Communication is tighly linked with Enterprise Environmental Factors (Org Structure). TT1: Total No of Comm Channels or Paths = n(n-1)/2 --- Comm Channels: # Upward Comm to Management # Lateral Comm to Peers, other Functional Groups and Customers # Downward Comm to Subordinates. TT2: Factors that can effect - 1. Urgency of the need for information 2. Availability of Technology 3. Expected Project Staffing 4. Duration of the Project 5. Project Environment. TT3: It consists of the following components - a Sender, a Receiver, Encode, Decode, a Medium (through which messages are send and received), Noice and Message & Feedback Message. TT4: 1. Interactive Comm - A. Formal Verbal (Presentations and Speeches), B. Informal Verbal (Meetings, Conversations, Humor, and Inquiries) 2. Push Comm - A. Formal Written (Proj. Plans, Charter, Comm over Long Distances, Complex Problems, Legal Docs and Long or Tech situations for a wide and varied audience), B. Informal Written (Status Updates, Information Updates and Day-to-day Comm., Email) 3. Pull Comm - for very large volumes of information, or for very large audiences (Internet Sites, E-learining and Knowledge Repositories. And are more likely to use Formal Written Methods)
PLANNING | 1. Stakeholder Register | 1. Communication Requirement Analysis | 1. Communications Management Plan
| 2. Stakeholder Management Strategy | 2. Communication Technology | 2. Project Document Updates
| 3. Enterprise Environmental Factors | 3. Communication Models
| 4. Organizational Process Assets | 4. Communication Methods
30 | Distribute Information: Execution of Comm Management Plan, as well as responding to unexpected requestss for information. It is the process of making relevant information available to project stakeholders as planned. It is performed according to Comm Management Plan, it is where the Bulk of Project Communication takes place. Communication methods: • Informal Written: Emails, memos. • Formal Written: Contract, legal notices, project documents. • Informal Verbal: Meetings, discussions, phone calls. • Formal Verbal: Speeches, mass communication, presentations. TT1: Individual and Group Meetings, Video and Audio Conferences, Computer Chats, and other remote comm methods. TT2: 1. Hard-copy document distribution, 2. Electronic Comm and Conferencing tools (Email, Fax, Voice Mail, Telehpne, Video and web Conferencing, Websites and Web Publishing), 3. Electronic Tools for Project Management (Scheduling & Proj Mgmt SW, Meeting and Virtual Office Support SW, Portals, and Collaborative Work Management Tools).
Executing | 1. Project Management Plan | 1. Communication Methods | 1. Organizational Process Assets Updates
| 2. Performance Reports | 2. Information Distribution Tools
3. Organizational Process Assets
31 | Manage Stakeholder Expectations: It is the process of communicating and working with stakeholders to meet their needs and addressing issues as they occur. It works to identify and resolve stakeholder concerns in a proactive and timely manner. It will be performed throughout the project. The Project Manger is responsible for stakeholder expectations management. Mgmt: 1. Actively managing the expectations, 2. Addressing concerns, 3. Clarifying and Resolving Issues.
EXECUTING | 1. Stakeholder Register | 1. Communications Methods | 1. Change Requests
| 2. Stakeholder Management Strategy | (Face-to-face is the best) | 2. Project Management Plan Updates
| 3. Project Management Plan | 2. Interpersonal Skills | 3. Project Document Updates
| 4. Issue Log (Action Item Log) (Each Issues should be assigned to one Owner) | 3. Management Skills | 4. Organizational Process Assets Upd
5. Change Log
6. Organizational Process Assets
32 | Report Performance: It involves collecting and disseminating Project Information, Communicating Progress, Utilization of Resources and Forecasting Future Progress and Status. It reports to the stakeholders how the project is progressing against the plan. Important note in Report Performance is that Performance Reports are actively pushed to stakeholders rather than waiting for them to pull them down. TT2: Forecasting Methods: 1. Time Series Methods - use historical data as the base (EV, Moving Average, Extrapolation, Linear Prediction, Trend Estimation, and Growth Curve), 2. Causal/Econometric Methods - use Assumptions (Regression analysis using Linear Regression or Non-linear Regression, Autoregressive Moving Average (ARMA), ARIMA, and Econometrics, 3. Judgmental Methods - incorporate intuitive judgements, opinions, and probability estimates (Composite forecasts, Surveys, Delphi method, Scenario building, Technology forecasting, and Forecast by analogy), 4. Other Methods (Simulation, Probabilistic forecasting, and Ensemble forecasting)
M & C | 1. Project Management Plan (Performance Measurement Baseline - It includes Cost, Schedule, Scope, Tech, and Other Baselines) | 1. Variance Analysis - Backward Looking Tool (It is an after-the-fact) | 1. Performance reports (It shows how the project is progressing against the various baselines (Scope, Time, Cost and Quality).
| 2. Work Performance Information (Deliverables Status, Schedule Progress, and Costs Incurred) | 2. Forecasting Methods - Forward Looking Tool (EAC, ETC) | Common Formats - Bar Charts, S-curves, Histograms, and Tables. Variance, EV, Forecasting.
| 3. Work Performance Measurements (CV, SV, CPI, CPIc, SPI) | 3. Communication Methods (PM generally uses a PUSH Comm Technique) | 2. Change Requests
| 4. Budget Forecasts | 4. Reporting Systems (Standard Tool for PM to Capture, | 3. Organizational Process Assets Updates
| 5. Organizational Process Assets | Store and Distribute Information)
# According to Kerzner - "90% of the Project Manager's time is spent communicating".
# Project Manager should be in control of Project Communication Management Plan.
# Communication on Schedule slippage, Cost overrun, and Other major Project Statuses should be FORMAL and in WRITING.
# Lessons Learned focus on Variance from the Plan and what would be done differently in the future in order to avoid these.

## Risk
RISK
Sl# | Inputs | Tools & Techniques | Outputs
33 | Plan Risk Management: The process of DEFINING HOW to conduct risk management activities for a project. In Plan Risk Management, the remaining FIVE risk management processes are PLANNED (creating a road map for them) and HOW they will be conducted is documented. Here focus will be on "HOW RISKS WILL BE APPROACHED ON THE PROJECT". # Risk Management Plan defines WHAT LEVEL of risk will be considered tolerable for the project, HOW risk will be managed, WHO will be responsible for risk activities, the AMOUNTS OF TIME and COST tht will be allotted to risk activities, and HOW risk findings will be COMMUNICATED. # Risk Breakdown Structure (RBS): It is not breaking down the actial risks, instead, we are breaking down the CATEGORIES of risks that we will evaluate.
PLANNING | 1. Project Scope Statement | 1. Planning Meetings and Analysis | 1. Risk Management Plan (It includes the following:
| 2. Schedule Management Plan |  | a) Methodology, b) Roles and Responsibilities, c) Budgeting, d) Timing, e) Risk Categories, f) Definitions of risk probability and impact, g) Probability and impact matrix, h) Revised stakeholders' tolerances, i) Reporting formats, and j) Tracking).
3. Cost Management Plan
4. Communications Management Plan
5. Enterprise Environmental Factors
6. Organizational Process Assets
34 | Identify Risk: The process of determining WHICH risks may affect the project and documenting their characteristics. # TT1: Documentation reviews is when you look at OPA and any documents to squeeze any possible risk out of them. # TT2: Most common Techniques are 1. Brainstorming, 2. Delphi Technique, 3. Expert Interviews, and 4. Root Cause Identification. # TT4: Assumptions analysis is when we look as project assumptions. # TT5: Diagramming Techniques: Ishikawa/Cause-and-effect/Fishbone Diagram, Influence Diagram, and System or Process Flow Charts. # TT6: SWOT: It is a tool to measure each RISK's SWOT. Each risk is plotted, and the quadrant where the Weekness (usually Internal) and Threats (usually External) are HIGHEST, and the quadrant where Strenghts (again, usually Internal) and Opportunities (usually External) are HIGHEST will present the HIGHEST RISK on the project.
PLANNING | 1. Risk Management Plan | 1. Assumptions Analysis | 1. Risk Register
| 2. Scope Baseline | 2. Checklist Analysis (it uses RBS) | (List of Identified Risks and List of Potential Responses)
| 3. Schedule Management Plan | 3. SWOT Analysis | It is a part of Project Documents.
| 4. Cost Management Plan | 4. Diagramming Techniques | Root causes, risk categories
| 5. Quality Management Plan | 5. Information Gathering Techniques | Responses are documented here as well.
| 6. Activity Duration Estimates | 4. Documentation Reviews
| 7. Activity Cost Estimates | 7. Expert Judgement
8. Stakeholder Register
9. Project Documents
10. Enterprise Environmental Factors
11. Organizational Process Assets
35 | Perform Qualitative Risk Analysis: The process of PRIORITIZING risks for further analysis or action by assessing and combining their probability of occurance and impact. # It is usually a RAPID and COST-EFFECTIVE means of establishing priorities for Plan Risk Responses and lays the foundation for Perform QUANTITATIVE Risk Analysis, if required. This process can lead into Perform Quantitative Risk Analysis or directly into Plan Risk Responses. # Qualitative risk analysis helps you prioritize each risk and figure out its probability and impact.
PLANNING | 1. Risk Register | 1. Risk Probability and Impart Assessment | 1.Risk Register Updates (Updates include: 1. Relative
| 2. Risk Management Plan | 2. Probability and Impact Matrix | ranking or priority list of project risks, 2. Risks grouped by categories, 3. Causes of risk or project areas requiring particular attention, 4. List of risks requiring response in the near-term, 5. List of risks for additional analysis and response, 6. Watchlists of low-priority risks, and 7. Trends in qualitative risk analysis results).
| 3. Project Scope Statement | 3. Risk Data Quality Assessment
| 4. Organizational Process Assets | 4. Risk Urgency Assessment
5. Risk Categorization
6. Expert Judgment
36 | Perform Quantitative Risk Analysis: The process of NUMERICALLY ANALYZING the effect of identified risks on overall project objectives. It relies on the prioritized list of risks from the Perform Qualitative Risk Analysis process. COST and SCHEDULE are easily quantified, and this process is concerned with quantifying the risks. SCOPE generally fits better into the Qualitative Risk Analysis. # TT1: 1. Interviewing, 2. Probability Distribution (Beta Distribution, Triangular Distribution). Uniform Distribution can be used if there is no obvious value (early concept stage of design). Probability Distributions are very useful for analyzing risks. # TT2: 1. Sensitivity Analysis (Tornado Diagram shows HOW SENSITIVE each analyzed area of the project is to risk. It ranks the bars from GREATEST to LEAST on the project so that the chart takes on a Tornado-like shape). 2. Expected Monetary Value Analysis (EMV): The EMV of OPPORTUNITIES will generally be expressed as POSITIVE VALUES, while those of THREATS will be NEGATIVE. EMV requires a Risk-Neutral assumption, neither risk averse, nor risk seeking. A common type is "Decision Tree Analysis". 3. Modeling and Simulation: Monte Carlo Analysis throws large numbers of scenarios at the schedule to see the impact of certain risk events.
PLANNING | 1. Risk Register | 1. Data Gathering and Representation Techniques | 1. Risk Register Updates
| 2. Risk Management Plan | 2. Quantitative Risk Analysis and Modeling Techniques | (Updates include 1. Probabilistic analysis of the project, 2. Probability of achieving cost and time objectives, 3. Prioritized list of quantified risks, and 4. Trends in quantitative risk analysis results)
| 3. Cost Management Plan | 3. Expert Judgment
4. Schedule Management Plan
5. Organizational Process Assets
37 | Plan Risk Responses: The process of DEVELOPING OPTIONS and ACTIONS to enhance opportunities and to reduce threats to project objectives. It creats a plan for HOW each risk will be handled. It assigns specific tasks and responsibilites to specific team members. Here, the ACTION PLANS for HOW Risks should be handled are determined. # TT1: Avoid - Undesirable Risks, Transfer/Deflect - to another party (Contractual Agreements and Insurance), Mitigate - to make it less, Accept (Negative/Positive) - best strategy may not be to Avoid, Transfer, Mitigate, Share, or Enhance it. Instead, the best strategy may be simply to Accept it and continue with the project. If the cost or impact of the other strategies is too greater, acceptance is the best strategy. # TT2: Exploit - trying to remove any uncertainty, Share - improve their chances of the positive risk occurring by working with another party, Enhance - first we have to understand the underlying cause(s) of the risk. By influencing the underlying risk triggers, you can increase the likelihood of the risk occurring. 1. Risk Register Updates: Resedual Risks, Secondary Risks, Contingency Plan, Risk Response Owners, Fallback Plans, Reserves/Contingency, and Risk Triggers.
PLANNING | 1. Risk Register | 1. Strategies for Negative Risks or Threats | 1. Risk Register Updates
| 2. Risk Management Plan | 2. Strategies for Positive Risks or Opportunities | 2. Risk-related Contract Decisions
| No O.P.A & E.E.F | 3. Contingent Response Strategies | 3. Project Management Plan Updates
|  | 4. Expert Judgment | 4. Project Document Updates
38 | Monitor and Control Risks: The process of IMPLEMENTING risk response plans, TRACKING identified risks, MONITORING residual risks, IDENTIFYING new risks, and EVALUATING risk process effectiveness throughout the project. #TT5: Focuses on functionality, looking at HOW the project has met its goals for delivering the scope over time. 1. Risk Register Updates: Outcomes of Risk Audits and Reassements, Identification of New Risks, Closing Risks that no longer applicable, Details what happened when Risks occurred, and Lessons Learned.
M & C | 1. Risk Register | 1. Risk Audits | 1. Risk Register Updates
| 2. Project Management Plan | 2. Risk Reassessment | 2. Change Requests
| 3. Performance Reports | 3. Reserve Analysis | 3. Project Management Plan Updates
| 4. Work Performance Information | 4. Status Meetings (Team Meetings) | 4. Project Document Updates
| No O.P.A & E.E.F | 5. Technical Performance Measurement | 5. Organizational Process Assets Updates
6. Variance and Trend Analysis

## Proc
PROCUREMENT
Sl# | Inputs | Tools & Techniques | Outputs
39 | Plan Procurements: The process of documenting project purchasing decisions, specifying the approach, and identifying potential sellers. (How, What, How Much and When) * Document Make/Buy decisions and define the purchasing approach. * Buyers Risk (from Highest to Lowest) - CPFF - T&M - CPIF - FPIF - FFP * Commonly used & Preferred Type - FFP * Direct Cost or Out-of-Pocket Cost * RFI - Request for Information * IFB - Invitation for Bid * RFB/P - Request for Bid/Proposal * RFQ - Request for Quotation (Proc Docs) * IFB or RFB/P used for 1. Single Price, 2.High $ Value, 3. Standardized * RFQ used for 1. Per Item/Hour Price, 2. Lower $ Value, 3. May be used to develop info in RFP
PLANNING | 1. Requirements Documentation | 1. Make-or-Buy Analysis | 1. Procurement Management Plan
| 2. Teaming Agreements | 2. Contract Types | 2. Procurement Statement of Work
| 3. Scope Baseline | 3. Expert Judgement | (Performance/Functions/Design)
| 4. Project Schedule |  | 3. Procurement Documents
| 5. Activity Cost Estimates |  | 4. Make-or-Buy Decisions
| 6. Cost Performance Baseline (Budget) |  | 5. Source Selection Criteria
| 7. Activity Resource Requirements |  | 6. Change Requests
8. Risk Register
9. Risk-Related Contract Decisions
10.Enterprise Environmental Factors
11. Organizational Process Assets
40 | Conduct Procurements: The process of botaining seller responses, selecting a seller, and awarding a contract. * Receive responses from potential sellers and award the contract to the selected seller. * It carries out the Procurement Management Plan, select one or more sellers and award the procurement, usually in the form of a Contract. * It is the process of obtaining Seller Responses, Selecting a Seller/Sellers and Awarding Contract.
EXECUTING | 1. Project Management Plan (Pr M Pl) | 1. Advertising | 1. Selected Sellers
| 2. Project Documents | 2. Internet Search | 2. Procurement Contract Award
| 4. Procurement Documents | 3. Bidder Conference (Vendor/Pre-bid/Contractor) | 3. Resource Calendars
| 3. Teaming Agreements (Master Services Agreement) | 4. Proposal Evaluation Techniques | 4. Change Requests
| 5. Make-or-Buy Decisions | 5. Independent Estimates ('Should-Cost' Estimate) | 5. Project Management Plan Updates
| 6. Source Selection Criteria | 6. Procurement Negotiations | 6. Project Document Updates
| 7. Qualified Sellers' List | 7. Expert Judgement
8. Seller Proposal
9. Organizational Process Assets
41 | Administer Procurements: The process of managing procurement relationships, monitoring contract performance, and making changes and corrections as needed. * Manage the relationships, monitor performance and make changes as necessary. * The buyer and seller review the contract and the work results to ensure that the results match the contra contract. * Manages any early terminations of the contract work (for Cause, Convenience or Default) in accordance with the Termination Clause in Contract.
M & C | 1. Project Management Plan | 1. Inspections and Audits | 1. Procurement Documentation
| 2. Procurement Documents | 2. Procurement Performance Reviews | 2. Change Requests
| 3. Contract | 3. Performance Reporting | 3. Project Management Plan Updates
| 4. Approved Change Requests | 4. Contract Change Control System | 4. Organizational Process Assets Updates
| 5. Performance Reports | 5. Payment System
| 6. Work Performance Information | 6. Claims Administration
7. Records Management System (Indexing, Archiving, and Information Retrieval Systems)
42 | Close Procurements: The process of completing each project procurement. * Finalize and Close each purchasing contract. * When the contract is Completed or Terminated for any reason, this process is performed.
CLOSING | 1. Project Management Plan | 1. Procurement Audits (Review of Procurement Processes - for capturing Lessons Learned) | 1. Closed Procurements
| 2. Procurement Documentation | 2. Negotiated Settlements | 2. Organizational Process Assets Updates
3. Records Management System
# FFP - Risk is entirely shifted to the SELLER. It is very popular 'When the Scope of work is throughly defined & completely known'.
# FPIF - Point of Total Assumption (PTA) is a point in the contract where a subcontractor assumes responsibility for all additional costs. PTA = Target Cost + ((Ceiling Price - Target Price + Fixed Fee (if it is there)) / Buyer's % share of cost overrun)
# FP-EPA - Fxied Price with Economic Price Adjustment. It is popular where Fluctuations in Exchange Rates and Interest Rates. Economic Stipulation may be based on the Interest Rates, the Consumer Price Index, Cost of Living Adjustments, Currency Exchange Rates or other Indices.
# T&M - The Buyer bears the most risk of Cost overruns. It is used when the SCOPE of work is not completely defined.

## ImpPoints-1
IMPORTANT POINTS - 1
Sl# | Point to remember
1 | EEF & OPA must be taken into account for every process, even if they are not explicitly listed as inputs in the process specification.
2 | Project Management Team Activities: 1. Analyze and understand the scope. That includes the project and product requirements, criteria, assumptions, constraints, and other influences related to a project, and how each will be managed or addressed within the project. 2. Understand how to take the idetified information and then transform it into a project management plan using a structured approach. 3. Perform activities to produce project deliverables. and 4. Measure and monitor all aspects of the project's progress and take appropriate action to meet project objectives.
3 | Often the Scope, Schedule, and Cost Baselines will be combined into a Performance Measurement Baseline that is used as an overall Project Baseline against which integrated performance can be measured. The Performance Measurement Baseline is used for Earned Value Measurements.
4 | # Activities necessary for Administrative Closure of the Project or Phase, including step-by-step methodologies that address: 1. Actions and activities necessary to satisfy completion or exit criteria for the phase or project; 2. Actions and activities necessary to transfer the project's products, services, or results to the next phase or to production and/or operations; and 3. Activities needed to collect project or phase records, audit project success of failure, gather lessorns learned and archive project information for future use by the organization.
5 | # Configuration Management System (CMS): A CMS with Integrated Change Control provides a standardized, effective, and efficient way to centrally manage approved changes and baselines within a project. CM is a systematic procedure that refers to change management. CM protects both the customer and the project staff. * CMS is a collection of formal documented procedures used to apply direction and control compliance of products and componenets with project requirements. * Is a subsystem of the PMIS. * Includes the processes that define how project deliverables and documents are controlled, changed, and approved. * In many areas includes the Change Control System. Configuration Management Activities: 1. Configuration Identification, 2. Configuration Status Accounting, and 3. Configuration Verification and Audit.
6 | # Fait accompli: An accomplished fact; an action which is completed before those affected by it are in a position to query or reverse it. The literal translation into English of this French phrase is a fact realized or accomplished - what might these days be called a done deal.
7 | # WBS: WBS a deliverable-oriented hierarchical decomposition of the work to be executed by the project team. The WBS is finalized by establishing Control Accounts for the work packagess and a unique identifier from a code of accounts. The WBS represents all product and project wori, including the project management work (This is sometimes called the 100% rule). # The WBS can be structured as an outline, an organizational chart, a fishbone diagram, or other method. # Different deliverables can have different levels of decomposition. # Excessive decomposition can lead to non-productive management effort, inefficient use of resources, and decreased efficiency in performing the work. # Decomposition may not be possible for a deliverable or subproject that will be accomplished far into the future.
8 | # Work Performance Information: Focus on WHAT has been done (provideds information on the Status of a Deliverables).
9 | # Performance Reports: Focus on HOW it was done. (Focus on Cost, Time, and Quality performance). Here Actual Results are compared against the Baselines to show how the project is performing against the Plan.
10 | # Project Cost Baseline = Project Estimates + (Cost) Contingency Reserves; # Project Cost Budget = Project Cost Baseline + Management Reserves
11 | # Residual Risks comprise of 1. Risk that remain after applying risk response strategies, and 2. Risks that we simply ACCEPT - if it happens, it happens, we have a plan to deal with it.
12 | # Contingency Plans deal with the outcome of Residual Risks on project. # Contingency Resivers cover the outcome of Residual Risk, and account for the "Known Unknowns".
13 | # Fallback Plans are employed for Residual Risks when the Contingency Plans fail. # Secondary Risks are new risks that emerge as a result of Risk Response Plan.
14 | # Watchlist: All non-critical/non-top/low rating risks are put on the Watchlist and monitored(Watched) regularly. It is created at Perform Qualitative Risk Analysis Process. # Management Reservers account for the "Unknown Unknowns".
15 | # Utility Theory: An appropriate method for describing Risk Tolerance. * Risk Averse: Where there is more money at stake, the Risk Averter's satisfaction diminishes; he or she prefers a more certain outcome and demands a premium to accept projects of high risk. * Risk Neutral: Tolerance for risk remains the same as the money at sake increases. * Risk Seeker: The higher the stakes, the better; as risk increases, the risk seeker's satisfaction increases; he or she is even willing to pay a penalty to take on projects of high risks.
16 | # Force Majeure Risks, such as Earthquakes, Floods, Acts of Terrorism, Etc., should be covered under Disaster Recovery Procedures instead of Risk Management.
17 | # Monte Carlo Analysis would show you is WHERE SCHEDULE RISK EXISITS (Points of Schedule Risk). It is a Computer-based Analysis & useful for revealing Schedule Risks
18 | In accordance with the Planning process group, the order of processes are: develop project management plan, collect requirements, define scope, create WBS, define activities, sequence activities, estimate activity resources, estimate activity durations, develop schedule, estimate costs, determine budget, plan quality, develop HR plan, plan communications, plan risk management, identify risks, perform qualitative risk analysis, perform quantitative risk analysis, plan risk responses, and plan procurements.
19 | What is the meaning of a concept called the "Journey to Abilene"? Committee decisions can have the paradox outcome, that a jointly made or approved decision is not desired by any individual group member.
20 | What is a constructive change? A direction by the buyer or an action taken by the seller that the other party considers an undocumented change to the contract.
21 | Liquidated damages (LDs) are contractually agreed payments in order to… ...cover the customer's costs caused by late completion or failure to meet specifications by the contractor.
22
23
24

## ImpPoints-2
IMPORTANT POINTS - 2
Sl# | Introduction to Project Management
1 | A project is a temporary endeavor to create a unique product or service. Operations are ongoing activities.
2 | Progressive elaboration is the process of taking a project concept through to the project plan. As the planning and research activities continue, the more detailed and focused the concept becomes. Progressive elaboration happens throughout the project. It is the process of elements within the project becoming more and more exact as additional information and details become available.
3 | Milestones are not completed by the project manager, but by the project team. In addition, milestones are the results of activities, not activities themselves.
4 | Project closure is also known as the project postmortem.
5 | The project scope defines the required work, and only the required work, to complete the project.
6 | Scope verification is the proof that the project manager has completed the project.
7 | Whenever you have access to historical information, this is your best source of input.
8 | Quality policy is the organization-wide rules and requirements for quality.
9 | The project manager should use approved rewards and incentives to move the project team towards completion.
10 | An information retrieval system is paramount for a project with so much documentation. Technically, all projects should have an information retrieval system.
11 | The contract between the organization and the vendor supercedes all other work-related documents.
12 | Programs are a collection of projects with a common cause.
13 | Project Portfolio Management is the process of choosing and prioritizing projects within an organization. An excellent project idea can still be denied if there are not enough resources to complete the project work.
14 | Businesses exist to make money.
15 | Customers, internal or external, are the most important stakeholders in a project.
16 | Getting collective action from a group of people who may have quite different interests is 'Politics'.
17 | Generally, a difference in requirements resolved in favor of the customer. However, it is the project manager's responsibility to inform the customer of other options.
18 | The project management office can be established to offer services ranging from basic support to total management of all projects. Choice D covers the diverse opinions of management, and will meet all their needs.
19 | You might remember a similar question with a different answer. Operations and maintenance activities are not part of projects. The work to collect data, meet with operations and maintenance to explain the project, and other such activities should be included in the project.
20 | Management by objectives tries to focus all activities on meeting the company's objectives. If the project's objectives are not in line with the company's objectives, the project may be impacted or cancelled.
21 | The project coordinator reports to a higher-level manager and has authority to make some decisions. The project expediter has no authority to make decisions.
22 | The key word here is "cross-disciplinary." Cross-disciplinary means that the project covers more than one department or technical area of expertise. In such a case, a matrix organization is needed with representatives from each department or discipline.
23 | Effective project management requires a life cycle approach to running the project.
24 | The PMO determines whether a project supports the organization's strategic plan and can authorize exceptions to projects not linked to the strategic plan.
25 | The work of completing the product scope is accomplished during the executing process group.
26 | It is a responsibility of the project management office to prioritize the company's projects. When prioritization is clear, it is easier to allocate resources among projects.
27 | Notice that this question asks about product verification, not scope verification. The Verify Scope process occurs during project monitoring and controlling, and product verification is done during project closing.
28 | Deliverables are determined in part by the customer, but not the sponsor.
29 | The best answer is stakeholders, as their input is critical for collecting all the lessons learned on each project. The term "stakeholders" includes all the other groups
30 | The project manager or the project management team determines how best to accomplish the project.
31 | The organization has a direct influence on the project. A participative approach will probably not be as effective in a hierarchical organization.
32 | During the monitoring and controlling process group, project performance is measured, and needed changes are identified and approved.
33 | The project charter gives authorization to begin a project or project phase. The project charter is approved in the initiating process group.
34
35
Sl# | Examining the Project Management Framework
1 | The project life cycle is comprised of phases.
2 | The completion of a project phase may also be known as a kill point or stage gate. Kill points are typically at the end of a project phase. A kill point does not mean the project is killed, just that the potential for termination exists.
3 | Managing has to do with consistently producing key results that are expected by stakeholders.
4 | Email is not a Formal Communication.
5 | Arbitration is a form of negotiation. Technically, it is a form of assisted negotiation.
6 | To influence an organization (in order to get things done), a project manager must understand the explicit and implied organizational structures within an organization.
7 | Rumors and gossip can sabotage a project. This is an example of cultural achievability.
8 | Exit criterion are activities or evidence that allow a project to move forward. Stakeholder expectations are universal to the entire project, not just to one project phase.
9 | Projects typically have low costs and low demand for resources early in their life cycle. As the project moves closer to completion, the likelihood of risk diminishes
10 | Projects with much risk and reward are most likely to be accepted within an entrepreneurial organization.
11
12
Sl# | Examining the Project Management Processes
1 | A process is a series of actions bringing about a result. Recall that processes exist in projects and in project phases.
2 | Product-orientated processes are unique to the product the project is creating.
3 | Rolling wave planning is a description of the planning process in most large projects. It requires the project manager and the project team to revisit the planning process to address the next phase, implementation, or piece of the project.
4 | By involving the stakeholders at different aspects of the project, their requirements are more likely to be met. Specifically, scope verification ensures that the stakeholders are seeing that phase deliverables, project progress, quality, and expectations are being met.
5 | Organizational planning is the facilitating planning process which defines roles and responsibilities-and the reporting structure within the project.
6 | On a project with 45 key stakeholders, the project manager must work to manage stakeholder expectations. Given the impact of the project and the identified controversy, the project manager will need to proceed with caution to ensure the project deliverables meet the required expectations of the stakeholders.
7 | Projects fail at the beginning, not the end. A poor requirements document, inadequate needs assessments, unfulfilled planning, and more early processes can contribute to project failure.
8
9
Sl# | Project INTEGRATION Management
1 | Projects are selected based on business needs first.
2 | Change requests do not always require more money. Approved changes may require more funds, but not always. The change request may be denied, so no additional funds are needed for the project.
3 | A formal, documented change request is the best course of action for a change request stemming from a law or regulation. Integrated Change Control requires detail for implementing the change. Without evidence of the need for the change, there is no reason to implement it.
4 | The project sponsor can help the project manager and the stakeholders resolve issues during project integration management.
5 | If management has assigned the project constraint of a fixed budget, the project manager and the project team must determine how the project can operate within the constraint.
6 | Project plans communicate to the project team, the project sponsor, and stakeholders. Q: The primary purpose of your project plan is: A: To provide accurate communication for the project team, project sponsor, and stakeholders.
7 | A project baseline serves as a control tool. Project plan execution and work results are measured against the project baselines.
8 | Gantt charts are excellent tools to measure and predict the project progress, but are not needed during the project plan development process.
9 | A PMIS can assist the project manager the most during project execution. It does not replace the role of the project manager, but only serves as an assistant. It helps the project manager plan, schedule, monitor, and report findings.
10 | The project plan serves as a guide to all future project decisions.
11 | A configuration management is the documentation of the project product, its attributes and changes to the product.
12 | Integrated Change Control is a system to document changes, their impact, response to changes, and performance deficits.
13 | The project plan is the formal document used to manage and control project execution.
14 | General management skills, status review meetings, and Work Authorization Systems are the best tools described here that serve as part of the project plan execution.
15 | EVM, earned value management, is used throughout the project processes. It is a planning and control tool used to measure performance.
16 | A project manager must manage a project. If all activities are delegated, chaos ensues and team members will spend more time jockeying for position than completing activities.
17 | Configuration management involves making sure that everyone is working off the same documents and version.
18 | The schedule baseline is there for you to determine how the project is progressing. Follow your change management process, and continue to track against your baseline.
19 | Effective project integration usually requires an emphasis on: Effective Communications at key interface points.
20 | With everything going well on the project, the only choice that makes sense is to review the management plans for the project.
21 | The change control system must also include procedures to handle changes that may be approved without prior review, for example, as the result of emergencies.
22 | Only with formal acceptance can the project manager be sure the project work is really complete.
23 | All Technical Work is completed (means you are in Closing Process Group) on the project - the remaining thing is 'Completing Lessons Learned'.
24 | Because net present value is the value in today's dollars of different cash flows, the project with the highest NPV is the best one. The number of years is included in the NPV calculation.
25 | Integration can be done during Planning and Executing, but it is most important when you reach key interface points in the project. You must orchestrate the coming together of the results.
26 | The sponsor issues the project charter and so he or she should help the project manager control changes to the charter. The primary responsibility lies with the sponsor.
27 | Constrained optimization uses mathematical models. Linear programming is a mathematical model.
28 | Most often, projects outsourced outside of the country encounter communication and time zone barriers. The procurement process should have assured the project manager that the sellers were skilled.
29 | Directing (choice A) occurs while the project management plan is being created. During project executing, the project manager should be focused on integrating the work of others into a cohesive whole. This is more important than just coordinating (choice C) or leading (choice D).
30 | Whenever a large number of changes occur on a project, it is wise to confirm that the business case, as stated in the project charter, is still valid.
31 | Present Value (PV): We convert a future cash flow into a value today. This allows us to DIRECTLY compare two future cash flows.
32 | The larger the BCR, SPI and CPI the better. A project with high priority normally holds more senior commitment.
33 | Integrated change control requires coordinating changes across knowledge areas. For example, a proposed schedule change will often affect cost, quality, risk, and resources.
34 | Remember, the internal rate of return is similar to the interest rate you get from the bank. The higher the rate is, the better the return.
35 | Meeting the baseline is one indicator of project success.
36 | Recollections (of information) are less reliable than other documented results.
37 | Change Control Procedure might address how to handle changes, but does not reflect approved changes. Changes made via the change control system will be documented in some part of the project management plan and/or project documents.
38 | Remember, project length is incorporated when computing NPV. You would choose the project that provides the most value, in this case the project with the highest NPV.
39 | You want to capture data at the end of each phase of a project. If you wait until the end, you may forget important information.
40 | A work authorization system is used to coordinate when and in what order the work is performed so that work and people may properly interface with other work and other people.
41 | Q: When should the Project Baselines be changed? A: For all Approved Changes. Sometimes, certain classifications of changes get automatic approval on a project and do not need a change control board's approval. For example, in an emergency, changes should be made by the project manager without the change control board. Changes can be made to the baselines, but only when they are officially approved.
42 | The biggest problem is retaining team members until closure of the project. People start looking for their next project and leave before administrative closure is complete.
43 | It is the sponsor's role to determine objectives. These objectives are described in the project charter.
44 | The project charter is issued by the sponsor. The project manager may have a role in its creation.
45 | Once the change has been made by the Project Manager, you need to update the documents affected by the change; the project management plan and/or project documents.
46 | A project without a charter is a project without support.
47 | A poor communications management plan is not likely to cause the volume of changes in this instance.
48 | It is the project manager's responsibility to manage the project scope completion within budget and reserves.
49 | The project manager loses credibility and performance by using overtime.
50 | Before anyone can be notified, the change must be finished. That means looking for time, cost, quality, risk, resources, and customer satisfaction impacts.
51 | A single high-level executive can end an entire project if he or she is not satisfied with the results, even if that person has, by choice, been only tangentially involved in the project. It is critical to ensure that all of the final decision makers have been identified early in a project in order to ensure that their concerns are addressed.
52 | Before you can do anything else, you have to know what YOU are going to do. Developing the management strategy will provide the framework for all the rest of the choices presented and the other activities that need to be done.
53 | The change management process should be formal so changes don't "just happen." You manage them. You want them documented for historical purposes so there is an audit trail indicating why you made the changes.
54 | A project is complete when all work, including all project management work, is complete and the product of the project, not just deliverables, accepted. The lessons learned are project management deliverables.
55 | A change management plan includes the processes and procedures that allow smooth evaluation and tracking of changes.
56 | Only a work authorization system helps with integrating work packages into a whole. A work authorization system helps ensure that work is done at the right time and in the right sequence.
57 | Primary Responsibility of the Project Manager is 'Interact with others in a Professional Manner while completing the project'.
58 | The change control system should already have methods of making changes described.
59 | Half the project is done and half the cost has been expended. The answer is simple. Or is it? In fact, you do not know what was planned, so you cannot answer this question.
60 | All types of closure must make sure that the actual product of the project meets the requirements for the product.
61 | The Project Manager should offer your assistance without doing the work of the other Project Manager.
62 | Documents that serve as historical records for future projects' are collected throughout the project, but are only archived during the Close Project or Phase process.
63 | Outputs of the Close Project or Phase process include archives, lessons learned, and project closure. However, some project resources (people, computers, telephones) must be used to perform these closing activities. Once completed, the project can release its resources.
64 | A project manager should be looking at where changes are coming from and doing whatever is necessary to limit the negative effects of change on the project. He needs to find the root cause, so future changes may be avoided.
65 | One of the ways to check if a change should be approved is to determine whether the work falls within the project charter. If not, it should be rejected, assigned to a more appropriate project or addressed as a project of its own.
66 | A work authorization system (choice A) helps tell the team when work should begin on work packages. A change control system (choice B) helps track, approve or reject, and control changes. A project management information system (PMIS - choice D) helps the project manager know how the project is going. Only a configuration management system (choice C) addresses controlling documents.
67 | The project manager is an integrator. This is a question about your role as an integrator and communicator.
68 | All the project documentation goes into the archives. Therefore, it must be completed. The archive is the last thing to create before releasing the team.
69
Sl# | Project SCOPE Management
1 | Most change requests are a result of Value-added change. Value added change centers on adding some element that was not available to the project scope to reduce costs at scope creation.
2 | The project team member did not follow the change management plan's method of incorporating changes into the scope.
3 | The responsibility to ensure that the project work is authorized, contracted, and funded rests with the project manager.
4 | Scope statements must at least include the quantifiable criteria of cost, schedule, and quality metrics. The scope statement serves as a point of reference for all future project decisions.
5 | The stakeholders determine the project requirements and decide whether the project was a success.
6 | After the customer's input, the performing organization's project team is responsible for scope baseline preparation. The scope baseline includes the WBS, WBS dictionary, and project scope statement.
7 | Team buy-in is a direct result of the WBS creation process.
8 | The heuristic (rule of thumb) we use in project decomposition is 80 hours. It doesn't matter how experienced the team members are. You need this level of reporting to manage the project effectively.
9 | The project manager must facilitate a fair and equitable solution, but the customer is the first of equals.
10 | Decomposing: The important words here are "project work packages". This indicates that a WBS has already been created. If ithe question said "project deliverables," the answer would have been 'Creating a WBS'.
11 | The numbering system allows you to quickly identify the level in the work breakdown structure where the specific element is found. It also helps to locate the element in the WBS directory.
12 | A change request is the most effective way of handling the disconnect between what users actually want and what management thinks they want.
13 | A team member should have flexibility at the work package level to make some changes as long as they are within the overall scope of the WBS dictionary.
14 | Informal changes to project scope and plan are probably the chief cause of schedule slippage, cost overruns and project team member frustration. Effective scope control is critical to the success of a project.
15 | The project manager should validate with the customer that the change will add value, and then follow the change process.
16 | Much of the work on the project is dictated by the project scope statement. Any imprecision in such a key document will lead to differing interpretations.
17 | The scope management plan describes how requested scope changes will be managed.
18 | The level of uncertainty in scope increases based on the scale of effort required to identify all the scope. For larger projects it is more difficult to "catch" everything.
19 | Work not in the WBS is outside the scope of the project.
20 | Scope verification focuses on customer acceptance of a deliverable while product verification is focused on making sure all the work is completed satisfactorily.
21 | The Verify Scope process is done at the end of each phase of the project. If it is not done, you risk delivering something in the next phase that is not acceptable to the customer.
22 | You need to first understand the change before you can evaluate it. In this instance, verbal communication is not likely to provide enough information to evaluate. Once you understand the change, you can work with the team to determine the impact and options.
23 | A submittal that does not meet the requirements should not be accepted.
24 | Customers do not generally approve the project scope (what you are going to do to complete their requirements); instead, they approve the product scope (their requirements)
25 | Fait accompli - Commonly used to describe an action which is completed before those affected by it are in a position to query or reverse it.
26
Sl# | Project TIME Management
1 | GERT, Graphical Evaluation and Review Technique, allows for conditional advancement. GERT allows for branching and loopbacks.
2 | Subnets are often included in network templates to summarize common activities in a project.
3 | Soft logic allows the project manager to make decisions based on conditions outside of the project, best practices, or guidelines.
4 | Commercial duration estimating databases are valid resources to confirm or base time estimates upon.
5 | Parkinson's Law states that work will expand to fulfill the time allotted to it.
6 | Rather than bloat activities, projects should use contingency reserve. Contingency reserve is a portion of the project schedule allotted for time overruns on activities.
7 | A Gantt chart is a bar chart that represents the duration of activities against a calendar. The length of the bars represent the length of activities while the order of the bars represent the order of activities in the project.
8 | Milestone Schedule can also be called as Master Schedule.
9 | The arrow diagramming method does not support finish-to-finish of relationships.
10 | Project planning (choice A) would use both types of charts. Team members (choice B) need to see details and so they need a bar chart rather than a milestone chart. Risk analysis (choice D) COULD make use of both charts. A milestone chart is used instead of a bar chart for any situation where you want to report in a less detailed way (choice C). Bar charts can scare people with their complexity and often show too much detail to be worthwhile on a management level. Milestone charts are more effective for reporting to management.
11 | The critical path does not change if the scope is the same. A more aggressive deadline simply means the project is two weeks behind.
12 | The wider the range between the optimistic and pessimistic estimates in a three-point estimate, the more uncertainty the estimator has.
13 | In addition to the Project Management Plan, the project team must create "Management plans document how the team will manage on a more detailed level. Examples of management plans include project scope, schedule, cost, quality, and risk management plans".
14 | A Discretionary Dependancy in one that base on: Experience (Based on lessons we learned from past projects or from our past experience, we prefer to do activities in a certain order).
15 | Assuming the project manager is meeting the project objectives and constraints, sponsor approval of a detailed schedule (choice A) is not as critical as that of functional managers. The customer (choice D) does not need to approve the detailed project schedule, just the end date and any milestones they might impose. The team (choice B) would at least have provided their estimates. Getting functional managers to approve will also, indirectly get team members' approval. Remember that the book PMP® Exam Prep says to assume a matrix organization. If functional managers knew what each of their people were doing, the timeframe, and when their activities were on the critical path, resource problems would not be as frequent. Approval of the schedule by functional managers provides the most benefits.
16 | The question is really asking, "What is done after Estimate Activity Durations?" Schedule compression occurs before finalizing the schedule.
17 | Many people forget to make use of the tools of project management planning while the project work is ongoing. Do not make that mistake. A network diagram does help you track flow, but it should be the flow of the work, not information (choice A). The network diagram has nothing to do with cost (choice C) or reward systems (choice D). The network diagram helps you know when work on the project should be done and in what order.
18 | Think of what you would do in the real world. Many project managers just ask for more resources or more time (choices B and C),. Asking for an extension of time is generally the best thing to do only when scope is added to the project. Adding resources will add cost. Choice D should be the last choice. Compressing the schedule lets you get more done with the resources and time that you already have on the project. It is almost always the first thing to do when there is a delay generated from within the project.
19 | You must change the critical path inorder to shorten the project duration. In this case, both activity C and activity H are on the critical path. If you have a choice, all things being equal, choose the earlier option. Therefore, activity C is the best answer.
20 | Standard deviation is a range that an estimate can vary +/- from the mean. The project needs to be done in 40 days, and the schedule calls for 38 days, so the project float is 2 days. With a standard deviation of two days, the project will take 38 +/- 2 days, or 36 to 40 days. Therefore, project float could be 0 to 4 days. Standard Deviation tells you how unsure the estimate is.
21 | Leveling resources generally extends the schedule. Resource leveling refers to keeping the number of resources the same and letting time and cost be flexible.
22 | Corrective action is anything done to bring expected future schedule performance in line with the project management plan. Such action should always be an output.
23 | A milestone shows the completion of a series of activities or work packages. Therefore it takes no time of its own.
24 | Parametric estimating does not make use of estimates from the team.
25 | Project network diagrams are schematic displays of the logical relationships among activities.
26 | You do not necessarily need to change the schedule, unless, of course, the delay is more than the activity's float.
27 | The only certain impact of a scope change is a schedule change to shorten or lengthen subsequent activities.
28 | There is no reason to think the project is going well or poorly based solely on float.
29 | "Project management" software is not designed to do a good job of creating a WBS. It cannot create a complete project management plan, nor can it manage a complete project. It is designed to create and control schedules.
30 | More interdependencies on a project increase the need for communication.
31 | GERT is the only diagramming technique that allows loops.
32 | A heuristic is a rule of thumb. Examples are cost per line of code, cost per square foot of floor space, etc.
33 | The primary purpose of a network diagram is to show logical relationships.
34 | A Monte Carlo analysis provides the ability to compute the probability of completing a project on a specific day.
35 | When the project is completed early, the project manager should report that the project came in ahead of time and explain WHY. This is a success! If there was proper project planning, this should occur because an expected risk did not materialize.
36
Sl# | Project COST Management
1 | The learning curve allows the cost to decrease as a result of decreased installation time as workers complete more of the installation procedure. As the project team completes more and more units, the time to complete a hotel room should take less and less time.
2 | Value analysis/engineering is a systematic approach to find less costly ways to complete the same work.
3 | The cost management plan controls how cost variances will be managed.
4 | Funding limit reconciliation most likely will affect the project schedule, since work will need to be moved to when funds will be available.
5 | A Definitive Estimate: The most expensive to create (A great deal of work is needed to fine tune a project so that you can get a definitive estimate).
6 | The Project Budget and Baseline will not be finalized and accepted until the planning processes are completed.
7 | A Cost Management Plan contains a description of: The WBS level at which Earned Value will be calculated.
8 | The variable and direct costs are most affected by the size and scope of the project. Indirect costs are usually computed as a percentage of direct costs.
9 | Value analysis is a way of finding the least expensive way to do the work.
10 | The life cycle cost will provide the picture of the total cost of the project. It includes project costs and operations and maintenance costs.
11 | Training Costs: You are training the team on skills required for the project. The cost is directly related to the project and thus a direct cost.
12 | Fringe benefits are included in overhead and are part of indirect costs.
13 | A full-time team member who completes her work sooner than planned could be forced to wait for the start of her next activity. Since she is full time, she would have to be paid for time not working.
14
Sl# | Project QUALITY Management
1 | The project team (the individuals completing the project work) is responsible for the quality of the project deliverables.
2 | Internal failure cost is attributed to failure that results in rework. It is an example of the cost of nonconformance to quality.
3 | QC requires an inspection of the work results. While quality is planned into a project, inspections ensure it exists. QA is typically a management process.
4 | ISO 9000 is not a quality management system, but a system to ensure an organization follows its own quality procedures.
5 | Kaizen technologies are small changes to processes and products on a steady, continuous basis to save costs and improve quality.
6 | Quality, in regard to the project scope, is about completing the work as promised.
7 | Q: Optimal quality is reached at what point? A: When revenue from improvement equals the incremental costs to achieve the quality. E: Marginal analysis provides that optimal quality is reached when the cost of the improvements equals the incremental costs to achieve the quality.
8 | Design of experiments uses experiments and 'what-if' scenarios to determine what variables are affecting quality.
9 | Checklists are simple but effective quality management tools that the project manager can use to ensure the project team is completing the required work.
10 | Quality attributes are the measurements that determine if the product is acceptable. They are based on the characteristics of the product for which they were designed.
11 | Perform Quality Assurance involves determining whether standards are being followed. This would be the least effective, since it does not address the specific problem described in the question.
12 | The only choice listed that makes sense and is an official input to Perform Quality Assurance is choice C. This question is similar to others in this program but not exactly the same. You may also see this occur on your exam. Carefully read the questions!
13 | Data points outside the control limits indicate the process is out of control, and production should be stopped until a solution is found.
14 | nspections may be conducted at any level including the project team, and at any time throughout the product development. They are used to prevent defects from being delivered to the customer.
15 | Developing specifications should come from a technical expert. The only choice listed that meets that description is engineering. Not every question on the exam will require that a project manager do the work.
16 | Benchmarking is the common term for a performance measurement standard.
17 | Trend analysis examines project results over time to evaluate performance.
18 | The Perform Quality Assurance process is the process in which we do quality audits to make sure we are using the correct processes.
19 | Quality management should be performed regularly and in parallel with other planning processes throughout the project.
20 | A good project manager will find the root cause and deal with that, even if it means attempting to improve the company's policies and processes. This is continuous improvement. Because there are several activities affected by the policy, it would serve the project better to get to the root cause of the problem and solve it.
21 | DOE: Proper design allows you to find those factors that have the most impact on quality. It allows the project manager to focus attention on the factors that are most important.
22 | Even though it is occurring during the execution of the project, determining what standards to use is part of quality planning. We sometimes need to fall back into planning during other parts of a project. In planning, we determine what quality standards are applicable to the project and how to implement and control them.
23 | Standard deviation is the measurement of a range around the mean.
24 | The control limits are more constraining than the specification limits. Control limits are how you measure your process quality. Specification limits are how the customer measures quality.
25 | The fishbone diagram is a tool that we use to help stimulate thinking (brainstorming), to create an atmosphere conducive to open sharing of thoughts, and to gather our thoughts in a cohesive way. It can be used during analysis to determine the cause of defects.
26 | This can be a tricky question, in that most project managers dismiss the need to focus on quality. Quality, cost, and schedule should be considered of equal importance unless specific project objectives make any one of them most important. Quality, cost, schedule, scope, risk, and other factors may be prioritized differently on each project.
27 | Although quality planning usually occurs during project planning, sometimes we need to go back to planning from other processes to make a decision.
28 | As you increase quality, there will be associated benefits for the project. Some of these benefits are increased productivity, increased cost effectiveness, decreased cost risk, and improved morale.
29 | A data point that requires you to determine the cause of the problem calls for a special cause.
30 | The control limits are set based on the company's quality standard and indicate the acceptable range.
31 | Discovering non-value activities is part of process analysis: implementing the process improvement plan. Many people choose to perform a quality audit (choice C). However, performing a quality audit relates to determining whether you are using the right processes and whether those processes are effective, rather than improving processes.
32 | The group is using organizational process assets to improve their project. Although the incident just occurred, it was on another project. They are in the Plan Quality process.
33 | You can use the WBS (choice C) in many ways to control quality.
34 | Inconsistency and nonpredictability are indications that the process is out of control.
35 | Having an allowable defect rate is an example of the cost of non-quality. Any system or process that will accept defects adds cost to the product or service.
36
Sl# | Project HR Management
1 | When projects are similar in nature, the project manager can use the roles and responsibilities definitions of the historical project to guide the current project.
2 | When project managers, or managers in general, are referred to as different terms, a job description is needed so the project manager can successfully complete the required obligations.
3 | The halo effect is the assumption that because the person is good at a technology they’d also be good at managing a project dealing with said technology.
4 | Q: Susan is the project manager for the PMG Project. She makes all decisions on the project team regardless of the project team objections. This is an example of which of the following management styles? A: Susan is an autocratic decision maker.
5 | When Harold always has to win an argument and team members begin to give into Harold’s demands simply to avoid the argument rather than to find an accurate solution, this is a yield-lose situation.
6 | The Expectancy Theory describes how people will work based on what they expect because of the work they do. If people are rewarded because of the work they complete, and they like the reward (payment), they will continue to work.
7 | Forcing happens when the project manager makes a decision based on factors not relevant to the problem. Just because a team member has more seniority does not mean this individual is correct.
8 | A reward and recognition system involves formal management action to promote desired behavior of individuals.
9 | Remember that confronting means problem solving and problem solving is the best way to resolve conflict ? but not here. The question asks "what conflict resolution technique would you IMMEDIATELY use with the team members." Tempers are too hot and you have the sponsor to deal with. The best immediate choice here is avoidance.
10 | There is always the option to simply postpone dealing with the issue until later. This is withdrawing.
11 | Notice that this question talks about what the team member should do? It is important for the project manager to understand the team member's role and possibly even instruct team members on how to work on projects and what is expected of them. Choices A, B, and C have one thing in common. They involve the team member asking the project manager to do something. In reality, it may very well be the team member who will come up with a solution (such as decreasing the scope of the activity, fast tracking, or specific suggestions about changes to predecessor activities). Therefore, choice D is the best choice. But ask yourself how you run your projects. Which is better, your way or this way? Lastly, please note that recommended corrective or preventive actions can come from the team or stakeholders in addition to the project manager.
12 | Keep in mind that the staffing management plan is created as part of Develop Human Resource Plan and updated as part of Acquire Project Team.
13 | A project manager can rarely tell or direct that project resources be assigned. Most frequently on projects, the functional manager owns the resources.
14 | Staffing Management Plan: WHEN and HOW resource will be ADDED and TAKEN OFF the team.
15 | A project charter is created during project initiating. A project manager is assigned during project initiating, not after it.
16 | A histogram is a bar chart where each bar represents the percent of time the resource is working. Each bar shows one unit of time (e.g., a week, a month, etc.). It does not show usage for each activity or area of expertise. The histogram is a set of bars that depict when a resource is being used, and to what level.
17 | A corner office is a "perk" whereas health benefits are a fringe benefit.
18 | Training: The project manager must ensure that the necessary skills are developed as part of the project.
19 | The tools and techniques of the Manage Project Team process are observation and conversation (watch the team and report on team members' performance), project performance appraisals (do a 360-degree feedback session), conflict management (use appropriate conflict resolution techniques) and issue log.
20 | Smoothing will emphasize that everyone agreed on a plan and that the team should have confidence in that plan.
21 | The role of each stakeholder is determined by: The Project Manager and The Stakeholder.
22 | Top four sources of conflict: schedules, project priorities, resources, and technical opinions
23 | Project performance appraisals deal with how each team member is performing work, rather than how well the team is working together.
24 | Mentoring: is the work that a project manager may be frequently called on to perform.
25 | Resource leveling refers to maintaining the same number of resources on the project for each time period. Leveling has nothing to do with assigning activities or managing meetings.
26 | After a team member completes project work, it is the project manager's job to provide input to the team member's manager regarding performance appraisals.
27 | Performance issues are senior and functional management's responsibility - usually the manager who supervises the resource.
28 | Functional management is responsible for addressing individual performance problems.
29 | Projects often need their own reward systems to affect performance. Project managers should create such a system for each project.
30 | Generally, the best forms of power are reward or expert. The project manager has not had time to become a recognized expert in the company (choice D) and reward is not included as a choice here. This leaves formal power (choice A) as the only logical answer.
31 | Halo Effect: It refers to the tendency of "Move people into Project Management because they are good in their technical field". (Just because a person is good in his technical field does not mean he will also be a good project manager).
32 | Technical issues of the project are managed by the team members' managers (Functional Managers).
33 | A project organizational chart shows resources and their responsibilities.
34 | A reward needs to be specific to the activities at hand to maximize the effect. Although the existing company reward system (choice A) may work, one created specifically for the project will address project-specific objectives and motivators.
35 | The final steps of problem solving include: implement a decision, review it, and confirm that the decision solved the problem.
36
Sl# | Project COMMUNICATIONS Management
1 | Communications Management Plan details the requirements and expectations for communicating information among the project stakeholders.
2 | A communication matrix is an excellent tool to identify the stakeholders and their requirements for communication.
3 | The figure is called a communications bull’s eye and is used to trigger communication needs to management when EVM results fall within the identified ranges.
4 | Paralingual is a term used to describe the pitch and tone of one’s voice.
5 | An exception report is typically completed when variances exceed a given limit.
6 | Administrative closure should take place at the completion of each phase. Administrative closure is the process of generating, gathering, and disseminating project information.
7 | Project meetings should have a set time limit.
8 | Conflict is not a filter of communication—it is a communication hindrance.
9 | Mutual respect and cooperation is the environment needed for fair and balanced negotiations. Collaborating is the ideal method when negotiating. The goal of negotiations is to work together for the good of the project.
10 | When information is sent, it is considered to be transmitted.
11 | The transfer of knowledge is evidence that communication has occurred.
12 | Report Perfromance is a monitoring and controlling process, and is also done during closure to report the performance of the project in the final report.
13 | Expectations are unspoken requirements and are often more critical to a project's stakeholders than the stated ones. Unless these expectations are identified and recorded, there is likely to be a high level of dissatisfaction with the project.
14 | The work breakdown structure (WBS) allows communication vertically and horizontally within the organization as well as outside the project.
15 | A user of the project's product is always a stakeholder, while the others may or may not be.
16 | Working with people from different cultures, with different cultural values and beliefs necessitates an understanding both basic definitions and the areas of cultural impact. As project managers, we need to have good communication skills and a willingness to adapt to other cultures.
17 | Gathering Information is a part of Communication Plan: With proper planning, you will be able to communicate effectively and accurately. In this case you are not gathering the correct information needed to report to the client.
18 | Understanding the receiver's perspective allows you to direct the communication to meet his needs.
19 | Project Manager wants to more extensively involve the Stakeholders on the project: Have the Stakeholders periodically review the list of Project Requirements.
20 | The overriding measurement of what information to accumulate and communicate on a project is whether that information contributes to the success of the project. The required information would take time away from the project and not provide added value.
21 | Aid to solve complex problems, written communication is the best: Written communication allows your words to be documented, and they will go to everyone in the same form. When there are complex problems, you want everyone to receive the same thing.
22 | Nonverbal communication carries 55 percent of the message you send. With this much at stake, nonverbal communication is of major importance.
23 | The bar chart is the tool that shows the schedule at a detailed enough level for discussion with the team.
24 | To ensure clear, concise communications, the project manager must manage communications by deciding what form of communication is best.
25 | Because of the differences in culture and the distance between team members, formal written communication is needed.
26 | Progress Reports generally show problems after they have occurred.
27 | Stakeholders can be identified throughout the project management process groups.
28 | Lateral Communication - Information exchange between the project manager and his/her peers: functional managers, staff personnel, contractors, other project managers, etc. Involves negotiating resources, schedules, and budgets; coordinating activities between groups, as well as developing plans for future operating periods.
Sl# | Project RISK Management
1 | An error value of seven percent represents the threshold the project is allowed to operate under. Should the number of errors increase beyond seven percent, the current plastic will be substituted. Q: A project manager and the project team are actively monitoring the pressure gauge on a piece of equipment. Sarah, the engineer, recommends a series of steps to be implemented should the pressure rise above 80 percent. The 80-percent mark represents what? A: The threshold - The 80-percent mark is a threshold.
2 | The utility function describes a person's willingness to tolerate risk.
3 | When the scope has been changed, the project manager should require risk planning to analyze the additions for risks to the project success.
4 | Monte Carlo simulations can reveal multiple scenarios and examine the risks and probability of impact.
5 | # Force Majeure Risks, such as Earthquakes, Floods, Acts of Terrorism, Etc., should be covered under Disaster Recovery Procedures instead of Risk Management.
6 | # Monte Carlo Analysis would show you is WHERE SCHEDULE RISK EXISITS (Points of Schedule Risk). It is a Computer-based Analysis & useful for revealing Schedule Risks
7 | Notice how many choices are half right? Monte Carlo could help you know that an estimate for an activity needs to change, but not what the activity estimate should be (choice B). Monte Carlo is a simulation (choice C) but it simulates time, not order of activities. Monte Carlo can be used to prove things to management (choice D) but its main focus deals with time, not staff. Risk can be assessed using Monte Carlo analysis (choice A). By considering the inputs to the PERT estimates and the network diagram, you can obtain a better overview of the overall project risk.
8 | # Workaround is what you do if the RISK OCCURS, but it does NOT REDUCE THE RISK.
9 | A decision tree allows you to make an informed decision today based on probability and impact analysis. You can decide based on the expected monetary value of each of your options.
10 | The range of estimates with the smallest range is the least risky.
11 | A risk rating matrix is developed by a department or a company to provide a standard method for evaluating risks. This improves the quality of the rating for all projects. A risk rating matrix is created during the Perform Qualitative Risk Analysis process.
12 | If you cannot determine an exact cost impact of the event, use qualitative estimates such as Low, Medium, High, etc.
13 | Prioritized risk ratingsare an input to the Plan Risk Responses process.
14 | First, you should evaluate the impact of the change. Next, determine options. Then go to management and the customer.
15 | The Risk Owner should be looking for triggers and implementing the risk response strategy.
16 | # Expected monetary value (EMV) is computed by EMV = Probability x Impact. We need to compute both positive and negative values and then add them. 0.6 x $100,000 = $60,000. 0.4 x ($100,000) = ($40,000). Expected Monetary Value = $60,000 - $40,000 = $20,000 profit. # The expected monetary value takes into account the probability and the impact. The calculation is: (0.05 x 21) + (0.5 x 56) - (0.3 x 28) The last part is subtracted because it represents an opportunity and should be balanced against the threat.
17 | The risk response owner is assigned to carry out responses and must keep the project manager informed of any changes.
18 | # Force majeure is a powerful and unexpected event, such as a hurricane or other disaster.
Sl# | Project PROCUREMENT Management
1 | A fair contract shares a reasonable amount of risk between the buyer and the seller.
2 | A bonus to complete the work by August 30 is an incentive.
3 | Privity is a confidential agreement between the buyer and seller.
4 | An SOW can be a contract if both parties agree to the SOW and sign the document as a contract.
5 | A single source seller means there is only one seller the company wants to do business with.
6 | An IFB is typically a request for a sealed document that lists the seller’s firm price to complete the detailed work.
7 | Procurement documents detail the requirements for the work to ensure complete proposals from sellers.
8 | For immediate work, a letter contract may suffice. The intent of the letter contract is to allow the vendor to get to work immediately to solve the project problem.
9 | A unilateral form of a contract is simply a purchase order.
10 | We decompose the Project using a WBS.
11 | The product description defines the details and requirements for acceptance of the project. This information also serves as a valuable input to the process of determining what needs to be procured. The product description defines what the end result of the project will be. When dealing with vendors to procure a portion of the project, the work to be procured must support the requirements of the project’s customer.
12 | Contracts are legal documents and, therefore, generally require more sign-offs.
13 | In a fixed price contract, the seller has the cost risk and therefore wants to completely understand the contract statement of work before bidding.
14 | Look again at the question. Ask yourself "How many computers does the contract say?" Did you read it as twenty (25)? This is an example of a conflict in the contract. The intent of the contract can be determined by remembering that words are more binding than numbers. Therefore, you should return the five extra computers.
15 | You need to encourage the client to realize that they have a problem and to finalize their requirements.
16 | As the project manager, you know what the project risks are. You need to make sure that provisions are included in the contract to address these risks.
17 | The requirement to provide PMP certified project managers is a screening system. A system to minimize personal prejudice is a weighting system.
18 | This is an example of privity. Because Companies A and C have no legal relationship, Company A cannot direct Company C. The smart thing to do is for the project manager of Company A to call the project manager from Company B, and have him communicate the directive from Company A.
19 | The project manager should attend the bidder conference.
20 | Procurement is a very formal process. Changes need to be fully documented and signed by both parties.
21 | Remember that PMI's definition of an audit is different. According to PMI, audits are used to improve the processes.
22 | Changes in resources used would generally not be part of a fixed price contract.
23 | If the seller completes the work specified in the procurement statement of work, the contract is considered complete. That does not mean the same thing as the procurement being closed. The Close Procurements process must still occur. However, in this situation, the contract work is completed. Tricky!
24 | Contract that limits fees for large projects with limited scope definition is cost plus fixed fee.
25 | There are certain basic things that should go into all contracts; an arbitration (or dispute resolution) clause is one of them. Imagine a situation where you have a dispute, but no plan already agreed to in the contract!
26 | If the contract is terminated, the project needs to enter closure. You need those results for historical purposes.
27 | It is not common for alternatives to be discussed at the bidder conference. They may be included in bids or proposals and discussed later.
28 | A customer's meeting minutes have no impact on disputes that arise; therefore, they are not required.
29 | A seller cannot issue a change order (although he could request one). Generally, only the buyer can terminate a contract.
30 | Terms and conditions should be the result of a risk analysis. This means the project manager has been assigned and has completed the risk management process before the contract is drafted. Contracts are risk mitigation tools!
31 | T & M Contract: Profit is factored into the hourly rate. Therefore, profit is increased for each hour worked. If many hours are used, profit can be higher than a fixed bid contract.
32 | The team members should not be requesting deliverables from the seller. However, since they did, you must pay for them and review the procedures with the team.
33 | Special provisions take precedence over general provisions.
34 | Any time that a seller does not perform according to the contract, the project manager must take action. The preferred choice might be to contact the seller and ask what is going on, but that choice is not available here. Therefore, the best choice is to let him know he is in default (choice C).
35 | The only way to change the cost plus fixed fee contract is to negotiate a change to the contract, normally in the form of change orders. Change orders should include an additional fee if additional work is added to the contract.
36 | Sellers are generally required under contract to keep working unless told otherwise.
37 | A procurement statement of work may be revised and refined as it moves through procurement.
38 | Did you notice that the question described change requests, not changes from other sources? Each of these change requests should be weighed to determine the benefits and the impact on the project. The criteria should be laid out in the procurement and change management plans. The best answer is to approve changes that benefit the project (choice C). For example, a change might cause a cost increase or schedule change, but still result in an overall benefit to the quality of the project.
39 | This is a large effort. No procurement statement of work can be developed, and expertise cannot be found internally. CPIF would be an incentive to the vendor to perform on or ahead of schedule.
40 | The contract change control system includes a method for controlling cost on the procurement.
41 | This situation is outside ofyour authority to control. You should therefore bring enough information to management that they can make a determination as to what to do.
42 | Workers Strike: The situation described is probably a force majeure. The appropriate response to a force majeure is to extend the contract.
43 | If it is not in the contract (which includes the specifications), a change order is needed to acquire it.
44 | Procrastination or a lack of planning on the part of the project manager does not create an emergency situation for the procurement manager.
45 | The project manager must be involved to protect the relationship between the company and the seller.
46 | The key to answering this question is to understand that this is a severe situation with many problems-so many problems that it is clear the contract is not serving either party. When a contract no longer serves the needs it was intended to serve, it can be renegotiated if the appropriate parties agree to this.
47 | When the seller has more expertise than the buyer, the procurement statement of work should describe performance or function rather than a complete list of work. In any case, the procurement statement of work should be as detailed as possible.
48 | Bidder conferences are held to provide all bidders a clear and common understanding of the work required.
49 | When you must begin work immediately without a procurement statement of work, the most appropriate choice is time and material.
50 | Seller has the patent for an item: If the seller goes bankrupt, you will no longer have a source for that material. You must deal with this risk.
51 | The buyer has the right to terminate the contract for cause or if the seller breaches the contract by not performing accordingly. Therefore, the procurement would enter the Close Procurements process. Any disputed payments or terms would be handled according to the dispute resolution procedures in the contract.
52 | The independent estimate is most concerned with cost, comparing cost estimates with in-house estimates, or with outside assistance.
53 | The most important issue is the level of detail in the procurement statement of work. If you have a design contract statement of work, a fixed bid contract is possible. Without this level of detail, the risk is high for the seller and thus the price is higher.
54 | Recognize that the procurement manager has power regarding the contract, while the project manager needs to look out for the specific needs of the project. This will cause conflict when the project's needs change and the procurement manager doesn't want to make changes.
55 | his question is asking for the output of the procurement process as a whole, not an output of the pieces within the process. The procurement process should lead toward formal acceptance (not the Contract) of the product of the project, making choice C the best choice. Be careful to properly read questions on the exam!
56 | A procurement audit includes what went right and wrong for the purposes of creating historical records and improving future performance.
57 | Here we are tying together the concepts of standard deviation and contracts. Using the concept of standard deviation, we find that the cost of this project will vary, at one standard deviation, from $1.8M to $2.2M. Since this is not insignificant, there would appear to be some ambiguity with the project definition. As we are not totally sure of the scope, we would not pick a fixed price option (choice A or C). Of the two CR options, you need to select the better of the two. Cost plus percentage of costs (choice D) is probably the worst type of contract to use, as there is no incentive for the seller to control costs. This leaves only choice B, a cost plus fixed fee contract.
58 | A letter of intent is not binding in a court of law, it does make the seller feel more comfortable about expending funds before a contract is signed.
59 | The time and material contract is the easiest to negotiate and allows for rapid turnaround. If you didn't have the time constraint, you would select a fixed price contract
60 | Generally in procurement situations, a change control board might review and approve or reject a change, but only the procurement manager has the authority to sign a change.
61 | Quality is defined as conformance to requirements. If inspection work is not performed as required in the contract, the project's quality standards are not being met.
62 | One factor in determining the contract type to use is the level of detail in the scope. In this case, we have little detail. A fixed price contract (choice C) is not the best due to the high risk to the seller and probable high cost bid. Therefore, a cost plus fixed fee gives the buyer the freedom to determine what they want while the contract is in process with no contract changes. The risk rests with the buyer.
63 | Due to the lack of detailed scope, you should not select a fixed price contract (choice A). Because the buyer wants to be in full control, the time and material contract (choice B) is the best option.
64 | In a procurement situation, generally only the procurement manager has the authority to sign changes. Sometimes the project manager has certain expanded authority to sign in the event of an emergency. However, an increase in cost is generally not considered an emergency.
65 | Once signed, a contract is binding. Generally, the inability to perform, get financing, or one party's belief that the contract is null and void does not change the fact that the contract is binding. If, however, both sides agree to terminate the contract, the contract can move into the Close Procurement process. Once closure is completed, the project is considered completed.
66 | Incentives are meant to bring the objectives of the seller in line with those of the buyer. That way both are progressing toward the same objective.
67 | In a Fixed Price Contract, the fee or profit is : Unknown (To the seller, it is known, but this question is from the buyer's perspective. You do not know what profit the seller included in the contract).
68 | The form of the deliverables for a specific portion of the project should have been reviewed and clarified during the Plan Procurements process.
69 | You always need to follow the change control process. You cannot arbitrarily decide to refuse to pay claims. Reserves should be used for identified risks and not used arbitrarily.
70 | The first thing that should come to mind is whether this is an ethical situation and whether it violates any company rules or laws. If it does not violate any of these, it would be best to check qualifications.
71
72
Sl# | PROFESSIONAL AND SOCIAL RESPONSIBILITY
1 | Professional and social responsibility requires the investigation of any instance where the legitimate interests of the customer may be compromised. If such a compromise is found, action must be taken.
2 | Diversity can enhance a project if planned and coordinated throughout the project.
3 | Whenever you are uncertain of whether a payment is a bribe, you should discuss the situation with legal counsel.
4 | You should offer your assistance to another Project Manager without doing the work.
5 | When the project is completed early, the project manager should report that the project came in ahead of time and explain WHY. This is a success! If there was proper project planning, this should occur because an expected risk did not materialize.
6 | The project manager is neither empowered nor competent to determine the legality of company procedures. NOTE: There is an important distinction between practices and procedures. All unethical practices should be reported. For example, a project manager must report an act of fraud. Fraud is not a company procedure (normally). However, a project manager is not in a position to determine whether company procedures comply with existing law.
7 | The project manager's responsibility is to provide truthful project information. He or she should thereafter discuss the impacts of their actions with the team members. If that does not work, the next step is to report it to their functional managers.
8 | Cultures are thought of as: Integrated wholes.
9 | Effective verbal communication: The Project Manager should always be as EXPLICIT, DIRECT, and UNAMBIGUOUS as possible given the cultural conditions.
10 | Performance Domains include: Planning, Executing, Controlling, and Professional Responsibility.
11 | The Code of Ethics and Professional Conduct advocates transparency in decision making, but it is not necessary for the Project Manager to take responsibility for all decisions.
12 | PMI does not condone deceit or competition without considering the needs of the organization.
13 | As the Project Manager, you have an obligation to report any unethical behavior. You may need to strategize with your sponsor before confronting anyone.
14 | In a Japanese cultural context, Project Managers would do best to focus on personal contact and relationship building before getting down to business.
15

## ImpPoints-3
IMPORTANT POINTS - 3
Sl# | Point to remember
1 | A project life cycle is a collection of generally sequential and sometimes overlapping project phases whose name and number are determined by the management and control needs of the organization or organizations involved in the project, the nature of the project itself, and its area of application.
2 | Parametric estimating uses a statistical relationship between historical data and other variables.
3 | Triggers. Indications that a risk has occurred or is about to occur. Triggers may be discovered in the risk identification process and watched in the risk monitoring and control process. Triggers are sometimes called risk symptoms or warning signs.
4 | Influence diagrams. These are graphical representations of situations showing causal influences, time ordering of events, and other relationships among variables and outcomes.
5 | When closing the project, the project manager will review all prior information from the previous phase closures to ensure that all project work is complete and that the project has met its objectives.
6 | Significant differences in cost estimates can be an indication that the procurement statement of work was deficient, ambiguous, and/or that the prospective sellers either misunderstood or failed to respond fully to the procurement statement of work.
7 | Since all other factors are kept at baseline values and only one element (i.e. currency rate) is changed, we are using Sensitivity Analysis. This can be shown using a Tornado diagram.
8 | Portfolio refers to a collection of projects or programs and other work (i.e. operations) that are grouped together to facilitiate effective management of that work to meet strategic business objectives.
9 | Teaming agreement:... The effort of the buyer and the seller in this process is to collectively prepare a procurement statement of work that will satisfy the requirements of the project. The parties will then negotiate a final contract for award.
10 | To evaluate the team`s effectiveness, we may include indicators such as: - Improvements in skills that allow individuals to perform assignments more effectively - Improvements in competencies that help the team to perform better as a team - Reduced staff turnover rate - Increased team cohesiveness whereby team members share information and experiences and help each other to improve the overall project performance To evaluate the team`s effectiveness, we do not consider the project delivery parameters like scope, time or cost.
11 | Milestone is a significant point or event in the project. Since milestones only indicate when a particular task is going to be started or completed, they will not have any duration, i.e., the duration for milestone is zero.
12 | During the project life cycle, the project team and key stakeholders identify lessons learned concerning all aspects of the project. The lessons learned are compiled, documented, and distributed so that they become part of the historical database. However, most of the organizations prefer post-implementation meetings and case studies to document lessons learned.
13 | In some cultures where offering gifts is a custom, rejecting or returning the gifts may be considered rude and inappropriate behavior. Appreciation of cultural differences is the way to win the trust of people from divergent cultures.
14 | Payback Period: 1. Number of years required for an organization to recapture an initial investment. 2. Discount rate is not taken into account in calculations of Payback Period, and 3. Project Selection Criterion: Select project with low Payback Period.
15 | In the project management context, integration includes characteristics of unification, consolidation, articulation, and integrative actions that are crucial to project completion, successfully managing stakeholder expectations, and meeting requirements.
16 | The areas to be considered in the process improvement plan include process boundaries, process configuration, process metrics, and targets for improved performance.
17 | In Estimate Activity Durations process, which of the following is not an assumption? A: Examples of assumptions include, but are not limited to, existing conditions, availability of information, and length of the reporting periods.
18 | The duration of the project should be calculated after drawing a network diagram and determining the critical path. The duration of the project is the length of the critical path and not the sum of the duration of all the tasks in the project.
19 | Since the change request pertains to a government regulation and the project is being managed as part of a contract, it is mandatory to implement the change. The first step towards that is to activate the change control mechanism.
20 | (Quality) Affinity diagrams are used to visually identify logical groupings based on natural relationships.
21 | (Quality) Force Field Analysis: Which are diagrams of the FORCE FOR and AGAINST CHANGE.
22 | A work authorization system is a collection of formal documented procedures that specifies how project work is authorized to ensure that work is done by the identified organization at the right time and in the proper sequence. Depending on the size of the project, the design of a work authorization system would vary. For example, on many smaller projects, verbal authorizations will be adequate.
23 | Organizational theory provides information regarding the way in which people, teams, and organizational units behave. Effective use of this information can shorten the amount of time, cost, and effort needed to create the human resource planning outputs and improve the likelihood that the planning will be effective.
24 | Identify stakeholders is the process of identifying all people or organizations impacted by the project, and documenting relevant information regarding their interests, involvement, and impact on project success... It is critical for the project success to identify the stakeholders early in the project, and to analyze their levels of interest, expectations, importance and influence. Identify Stakeholders is done as part of Initiating Process Group.
25 | The major difference between single source contracts and sole source contracts— though both are non-competitive forms of procurements— is that in single source contracts, contract is awarded to a seller because he is the organization’s preferred seller, where as in sole source contracts, contract is awarded to a seller because there are no other sellers for the organization’s required procurement item. Sole source contracts help organizations save time.
26 | There are multiple classification models(for stakeholders) available including, but not limited to: Power/interest grid, grouping the stakeholders based on their level of authority (power) and their level or concern (interest) regarding the project outcomes; Power/influence grid, grouping the stakeholders based on their level of authority (power) and their active involvement (influence) in the project; Influence/impact grid, grouping the stakeholders based on their active involvement (influence) in the project and their ability to effect changes to the project`s planning or execution (impact); and Salience model, describing classes of stakeholders based on their power (ability to impose their will), urgency (need for immediate attention), and legitimacy (their involvement is appropriate).
27 | A project life cycle is a collection of generally sequential and sometimes overlapping project phases whose name and number are determined by the management and control needs of the organization or organizations involved in the project, the nature of the project itself, and its area of application. Project can be broken into several phases, which can be done by using a life cycle approach.
28 | Schedule variance analysis along with review of progress reports, results of performance measures and modifications to the project schedule can result in change requests to the schedule baseline and/or to other components of project plan.
29 | The ability to influence cost is greatest at the early stages of the project, making early scope definition critical.
30 | Since this is a "minor flaw," but rectification of that flaw would take a long time, it is better to discuss with the sponsor and customer and get their inputs.
31 | ‘Prevention costs’ are costs incurred by an organization to create high quality products in order to avoid failures. They include cost of training, cost of documenting processes, cost of equipment, etc
32 | SMART Goals: The performance goals should be SMART - Specific, Measurable, Achievable/Attainable, Relevant and Time-specific.
33 | Preventive action: A documented direction to perform an activity that can reduce the probability of negative consequences associated with project risks.
34 | Trend analysis is performed using run charts and involves mathematical techniques to forecast future outcomes based on historical results. Trend analysis is often used to monitor technical performance, i.e., how many errors or defects have been identified, and how many remain uncorrected and cost and schedule performance, i.e., how many activities per period were completed with significant variances.
35 | Variance analysis is used to determine the cause and degree of variance relative to the schedule baseline and decide whether corrective or preventive action is required.
36 | Sequence Activities is the process of identifying and documenting the relationships among the project activities. Schedule network templates are the tools used in this process. (Scheduling tool) is used for Develop Schedule; (Decomposition) is used for Define Activities; (Schedule compression) is used for Develop Schedule
37 | Precision and accuracy are not equivalent. Precision means the values of repeated measurements are clustered and have little scatter. Accuracy means that the measured value is very close to the true value. Precise measurements are not necessarily accurate. A very accurate measurement is not necessarily precise.
38 | Inspections are sometimes called reviews, product reviews, audits, or walkthroughs. Stage gates are also referred to as phase-end reviews or kill points. They are different from Inspection.
39 | Some of the configuration management activities included in the integrated change control process are... configuration identification, configuration status accounting, and configuration verification and audit.
40 | Weight is the only variable here. All the other options refer to units of currency (Dollor, Pound) and measurement (Meters).
41 | Enterprise environmental factors may enhance or constrain project management options and may have a positive or negative influence on the outcome.
42 | Requests for change can be direct or indirect, externally or internally initiated, and can be optional or legally/contractually mandated. Request for change is always a formal process.
43 | Cancellation of the contract has to be done by both the seller and the buyer (i.e., the buyer cannot unilaterally cancel the contract).
44 | Definitive: - 5% to +10% accuracy Budgetary: -15% to +25% accuracy Order of magnitude: - 50% to +50% accuracy
45 | Project Management System: The aggregation of the processes, tools, techniques, methodologies, resources, and procedures to manage a project.
46 | Any time the customer requests for a change, you should: 1. Understand what kind of change is requested and talk with team members to assess the implication of the change. 2. Open up a change control if there is a formal change control mechanism. 3. Communicate the change to the management, and inform the customer about the impact of the change (e.g. increase in sizing, schedule, etc.). 4. Implement the change if it is accepted.
47 | The most preferred conflict resolution techniques adopted by project managers (in descending order of preference) are as follows: 1. Confrontation 2. Compromise 3. Smoothing 4. Forcing 5. Withdrawal
48 | Terms such as bid, tender, or quotation are generally used when the seller selection decision will be based on price (as when buying commercial or standard items), while a term such as proposal is generally used when other considerations such as technical capability or technical approach are paramount.
49 | A milestone list identifies all milestones and indicates whether the milestone is mandatory, such as those specified by contract, or optional, such as those based upon historical information.
50 | Due to varying organizational structures, many organizations treat contract administration as an administrative function separate from the project organization.
51 | People exhibit greatest resistance to change.
52

## ImpPoints-4
IMPORTANT POINTS - 4
Sl# | Point to remember
1 | Programs may often include 'Operations'.
2 | Sponsor - Project Champion.
3 | SMEs - Subject Matter Experts.
4 | Change Control System is a part of OPA (Organizational Process Assets).
5 | Outputs of all 42 Processes will be stored in PMIS.
6 | M & C Project Work: Activities - Measuring, Collecting, Inspecting, Questioning, and Assessing.
7 | M & C Processes' inputs are either PLAN or ACTUAL.
8 | All 10 M & C Processes have Change Requests as an output.
9 | Perform Integrated Change Control acts as 'Clearinghouse'.
10 | Project Management Software is a 'Means' not the 'End'.
11 | High Standard Deviation is High Risk.
12 | CPM - FLOAT usage; CCM - Buffer usage.
13 | PMI's 100% Rule - Complete SCOPE should be available in WBS.
14 | WBS: Graphical/Hierachical/Numerical
15 | Control Accounts - Performance Check Points/Management Check Points.
16 | Requirements Categories: 1. Product Requirements (Technical Specifications); 2. Project Requirements (Operational Specifications)
17 | Control Charts also called 'Shrewhart Charts'.
18 | Project Murder Board, which is defined as a panel of people who try to shoot down a new project idea. The other answers are also project selection methods, but they don’t explain why there is a panel of people that asks all of these questions.
19 | Observation and Conversation. This is also known as MBWA or Management By Walking Around.
20 | The conflict is of a technical nature, so the best way the project manager could solve the problem is by using his or her technical expertise.
21 | Forcing does do away with the conflict - but only temporarily. It is when the manager says that it is his project and you will do things his way. Period, end of discussion. The root of the problem is not addressed by this approach, thus the solution is only temporary.
22 | In Matrix Organization, the project manager is responsible for Manage Project Team.
23 | The standard deviation measures how diverse the population is. It does this by averaging all of the data points to find the mean, then calculating the average of how far each individual point is from that mean. For a very diverse population, you will have a high standard deviation. For a highly similar population, your standard deviation will be low.
24 | Job shadowing is also known as Observation, Quality Function Deployment is a facilitated workshop, and combined with surveys, these are all tools of the Collect Requirements process.
25 | Cause & Effect/Ishikawa/Fishbone Diagram or 5 WHY Technique.
26 | Quality Benefits must outweigh the Cost.
27 | LOW Standard Deviation means LOW Fluctuation; HIGH Standard Deviation means HIGH variation.
28 | Average Response Time should be less than TWO Hours.
29 | Perform Quality Control: - Inspecting; - Measuring; - Testing; - Charting; - Analyzing.
30 | Attribute Sampling is 'Binary' (Yes/No); Variable Sampling is Degree of Conformity.
31 | Inspection: Keeping errors out of the hands of the customer; Prevention: Keeping errors out of the process.
32 | Work Performance Measurements reveal actual results: * Condition of Deliverables; * Status of Schedule; * Status of Budget; * Performance Reports; * Technical Specifications. And it is a subset of WPI.
33 | The BIG Four: 1. Ishikawa; 2. Deming; 3. Juran; and 4. Crosby.
34 | The definition of the work authorization system is the system used to ensure that resources are formally being released to perform work at the right time and in the right sequence. In this case, a meeting with the resources’ functional manager would qualify as being a system.
35 | Leads and lags are APPLIED as part of the Develop Schedule process, but then they are ADJUSTED in the process of Control Schedule.
36 | In Verify Scope, the PM, sponsor, and customer inspect the product and verify that it meets the defined scope. ALL stakeholders are not involved in this process. Why not? There are too many stakeholders to seek acceptance from all; some stakeholders may be opposed to the project and never accept it! Don't confuse stakeholders with key stakeholders.
37 | The stakeholder register is used as an input in the following five processes: Collect Requirements (Scope), Plan Communications (Communications), Plan Quality (Quality), and Identify Risks (Risk). 'B' is the correct answer. This is an IMPORTANT input!
38 | A successful project manager will learn the art of delegation - what to delegate to others and what to not delegate. So, let's look at this list. 'A' - routine activities can be delegated - sure. The team will have regular responsibilities (routine tasks) that they are accountable for. 'B' - technical specs should be developed by the persons that have the expertise. That is probably not the PM. 'C' - picking the team-building activity for the next meeting - no problem. These first 3 can be delegated to the team. 'D,' however, should not be. The project manager is responsible for evaluations of team members. The PM should be providing feedback to the functional manager on the performance of staff. So, 'D' should not be delegated.
39 | You want to simulate the risk event (the server crashes and must be rebuilt) and determine the impact it has on the project. Think of this tool of Perform Quantitative Risk Analysis as you would a military drill or emergency drill. The team is thrown into a simulated, precarious situation and learns how to best respond. 'A' and 'C' are both tools of Perform Quantitative Risk Analysis but are not the correct choices here.
40 | Sensitivity analysis is the tool used when you want to evaluate how one change will affect the overall project. It works by keeping the other variables stable (that is, held at a baseline) and analyzing the impact of a change. Like sensitivity analysis, 'A' and 'B' are both tools of Perform Quantitative Risk Analysis; however, they are not a good match for the scenario provided. 'C' is a made-up term.
41 | This is a very realistic situation for most PMs. You should remember that face-to-face communication is always best and that team development should start early in the project - as soon as you have team members. This makes 'A' the best answer. 'C' includes incorrect information. Virtual teams are a tool of Acquire Project Team, not of Develop Project Team. 'B' is not the right answer because the policy doesn't state that no travel is allowed. Travelling to meet team members, as well as other stakeholders, is a realistic expense and not an extravagance.
42 | The Close Project or Phase process should be performed at the end of each phase or at the end of the project. It should also be observed early in the project to understand closure criteria from the very beginning of project planning. It is the process where the project is formally accepted and the project records are created. It is important to understand that Close Project or Phase may happen several times throughout the project.
43 | Team Building is Very Difficult in MATRIX, Very Easy in FUNCTIONAL, and next Esiest in PROJECTIZED.
44 | Risk SCORE will help guide Risk RESPONES.
45 | Zero Schedule Varience (SV) means the taks is completed.
46 | The more channels of communication on a project, the more difficult it is to control communications.
47 | The To-Complete-Performance-Index (TCPI) is: The cost performance index (CPI) required in the remainder of a project to meet financial goals.
48 | PMI prefers collaboration when it comes to resolving issues or conflicts. Some of the other answers are very tempting, but for the exam, focus on collaboration or either problem-solving confrontation as the best methods!
49 | It is the role of senior management to resolve organizational conflicts and to prioritize projects.
50 | Throughout the life of a project, a project manager should generally move through four phases of leadership: Directing, coaching, facilitating, and supporting.
51 | The Budget at Completion (BAC) and Planned Value (PV) can both be calculated before work begins.
52 | Configuration management is: A procedure to identify and document the functional and physical characteristics of an item or system.
53 | As part of integrated change control, the project manager will need to know when change has occurred, manage the changes, and influence the factors that cause change, but the project manager should not take on the attitude of denying change whenever possible. Some change is inevitable, and all change requests should be evaluated and not automatically rejected.
54 | The PMBOK Guide emphasizes the use of the configuration management system as it relates to managing and controlling change requests, specifically in the process of Perform Integrated Change Control.
55 | Prioritizing the changes is the job of the project manager.
56 | The S curve is the cost performance baseline. The cost performance baseline is used to track cost performance based on the original plan plus approved changes.
57 | An activity's late finish date is the latest an activity can finish without delaying the project. If it exceeds the late finish date, the critical path will change, ultimately resulting in the finish date slipping. Choice 'A' is close to the definition of free float.
58 | The contract change control system is defined in the contract, which is created as an output of the Conduct Procurements process, which is an executing process.
59 | The issue log is a tool used in Manage Project Team in the Human Resource Management knowledge area.
60 | There is a difference between present value and net present value. Present value tells the expected future benefits of the project in today's dollars. Net present value is very similar, but it also includes (or nets out) the expected future costs in today's dollars.
61 | Procurement performance reviews are a tool of Administer Procurements where the buyer arranges a meeting with the seller to review the seller's performance against the plan. This question presents a near-textbook case of this.
62 | If two events have no bearing on each other, they are statistically independent. Mutually Exclusive is when two events cannot both happen at the same time.
63 | A document management system is a configuration management tool, useful in the project management information system. Configuration information in particular will assist with the tool of Variance Analysis in the process of Control Scope.
64 | Resolving contract disputes is performed in Administer Procurements. However, when closing the contract, as in this case, the tool of Negotiated Settlements is used to settle any open claims, even if Alternate Dispute Resolution forms are invoked.
65 | The To Complete Performance Index is defined as the spending efficiency that is needed for the remainder of a project in order to meet a financial target or goal. If the goal is to complete the project on budget and the CPI is 90%, then the TCPI will need to be greater than 100% to compensate for the previous overruns. However, if the goal is amended to be the forecasted completion (EAC - which is derived from the CPI), then the current CPI will achieve the goal. Therefore, the TCPI equals the CPI for a target of EAC.
66 | Both the buyer and the seller perform Administer Procurements to ensure that all of the legal terms of the contract are being met by both parties.
67 | Until the scope has been defined and documented in the approved Scope Statement, WBS, and WBS Dictionary, which make up the scope baseline, it is not stable enough to be put under control.
68 | The tool being described is alternatives identification, used in the process of Define Scope. SMEs can help the project team brainstorm about the various creative ways that the project requirements might be accomplished.
69 | There is a difference between the product scope and the project scope. The scope of the project may be much larger than the scope of the product! The features and attributes that characterize a project deliverable or result describe which of the following? The product scope.
70 | Which of the following is the best description of a configuration management system? It provides a standard, efficient method to manage approved changes to baselines in a project.
71 | The definition of the work authorization system is the system used to ensure that resources are formally being released to perform work at the right time and in the right sequence. In this case, a meeting with the resources’ functional manager would qualify as being a system.
72 | TCPI: The completion of the remaining work at an actual cost not to exceed the remaining funds.
73 | Claims against the contracted parties should be filed as a result of a dispute, and resolving such claims is done in the process of Administer Procurements.
74 | The key phrase in this question is the sponsor's statement about achieving the budget goal. This should lead you to think of the To-Complete-Performance-Index. This index is the spending efficiency that you must maintain to achieve the stated goal, in this case, finishing the project on budget. TCPI=Remaining Work divided by Remaining Funds. Remaining Work is BAC-EV while Remaining Funds (with BAC as the goal) is BAC-AC. You are given AC and CV. EV=CV+AC so EV=$815K. Since you are 50% complete with the project, then BAC is twice the EV, or $1630K. Dividing remaining work ($815K) by Remaining Funds ($910K) gives you 89.6% which shows that Answer B at 90% is the best answer.
75 | In the Communications process of Identify Stakeholders, the PM leads the team to identify the project's stakeholders and the needs of the stakeholders. Stakeholder analysis is a tool of the Identify Stakeholders process.
76 | Soft skills such as interpersonal and management skills are important in relating to individuals, building trust, and delivering a clear message.
77 | Meetings are classified as informal verbal - even when the subject matter is important!
78 | Estimate Activity Resources outputs (primarily the activity resource estimates and the resource breakdown structure) are ideally created by the person doing the work. You would not necessarily need someone external to the project to review them.
79

## Ini & Clo
INTEGRATION
Sl# | Inputs | Tools & Techniques | Outputs
1 | Develop Project Charter:
INITIATING | 1. Project Statement of Work (SOW) | 1. Expert Judgment | 1. Project Charter (PC)
| 2. Business Case (is the document that justifies why the project should be accomplished) | a. Project Charter is created based on some need, and it should explain that need. | e. PC should include a high-level milestone view of the project schedule.
| 3. Contract | b. PC is signed by the performing organization's Senior Management. | f. PC is a high-level document that does not include project details; the specifics of project activities
| 4. Enterprise Environmental Factors | c. PC names the PM and gives PM authority to manage. | will be developed later.
| 5. Organizational Process Assets | d. PC should include the high-level proj requirements, high-level Project Description, high-level Risks. | g. PC includes a summary-level prelim project budget. h. Show organizational, environmental and external CONSTRAINTS and ASSUMPTIONS.
COMMUNICATIONS
28 | Identify Stakeholders:
INITIATING | 1. Project Charter | 1. Stakeholder Analysis | 1. Stakeholder Register
| 2. Procurement Documents | (Participation Analysis) | 2. Stakeholder Management Strategy
| 3. Enterprise Environmental Factors | 2. Expert Judgment | (Stakeholder Analysis Matrix)
4. Organizational Process Assets
INTEGRATION
6 | Close Project or Phase:
CLOSING | 1. Project Management Plan | 1. Expert Judgment | 1. Final Product, Service, or Result Transition
| 2. Accepted Deliverables |  | 2. Organizational Process Assets Updates
3. Organizational Process Assets
PROCUREMENT
42 | Close Procurements: The process of completing each project procurement. * Finalize and Close each purchasing contract. * When the contract is Completed or Terminated for any reason, this process is performed.
CLOSING | 1. Project Management Plan | 1. Procurement Audits (Review of Procurement Processes - for capturing Lessons Learned) | 1. Closed Procurements
| 2. Procurement Documentation | 2. Negotiated Settlements | 2. Organizational Process Assets Updates
3. Records Management System

## Exe
INTEGRATION
Sl# | Inputs | Tools & Techniques | Outputs
Direct and Manage Project Execution:
EXECUTING | 1. Project Management Plan | 1. Expert Judgment | 1. Deliverables
| 2. Approved Change Requests | 2. Project Management Information System - PMIS | 2. Work Performance Information (WPI)
| 3. Enterprise Environmental Factors |  | 3. Change Requests
| 4. Organizational Process Assets |  | 4. Project Management Plan Updates
5. Project Document Updates
SCOPE
TIME
COST
QUALITY
Perform Quality Assurance:
EXECUTING | 1. Project Management Plan (Q M Pl & Process Imp Pl) | 1. Quality Audits (Key Tool) | 1. Change Requests (for Procedural Changes)
| 2. Quality Metrics (Defines how Q will be measured) | 2. Process Analysis | 2. Project Management Plan Updates
| 3. Quality Control Measurements | 3. Plan Quality and Perform Quality Control Tools | 3. Project Document Updates
| 4. Work Performance Information | and Techniques | 4. Organizational Process Assets Updates
HUMAN RESOURCE
Acquire Project Team:
EXECUTING | 1. Project Management Plan | 1. Pre-Assignment | 1. Project Staff Assignments
| 2. Enterprise Environmental Factors | 2. Negotiation (Key Technique of this process) | 2. Resource Calendars
| 3. Organizational Process Assets | 3. Acquisition | 3. Project Management Plan Updates
4. Virtual Teams
Develop Project Team:
EXECUTING | 1. Project Staff Assignments (will have list | 1. Training | 1. Team Performance Assessments
| of all team members) | 2. Team-building Activities | 2. Enterprise Environmental Factors Upd
| 2. Resource Calendars | 3. Ground Rules
| 3. Project Management Plan | 4. Co-location
5. Recognition and Rewards
6. Interpersonal Skills (Soft Skills)
Manage Project Team:
EXECUTING | 1. Project Management Plan | 1. Observation and Conversation | 1. Change Requests
| 2. Project Staff Assignments | 2. Project Performance Appraisals | 2. Project Management Plan Updates
| 3. Team Performance Assessments | 3. Conflict Management | 3. Organizational Process Assets Updates
| 4. Performance Reports | 4. Issue Log | 4. Enterprise Environmental Factors Updates
| 5. Organizational Process Assets | 5. Interpersonal Skills
COMMUNICATIONS
Distribute Information:
Executing | 1. Project Management Plan | 1. Communication Methods | 1. Organizational Process Assets Updates
| 2. Performance Reports | 2. Information Distribution Tools
3. Organizational Process Assets
Manage Stakeholder Expectations:
EXECUTING | 1. Stakeholder Register | 1. Communications Methods | 1. Change Requests
| 2. Stakeholder Management Strategy | (Face-to-face is the best) | 2. Project Management Plan Updates
| 3. Project Management Plan | 2. Interpersonal Skills | 3. Project Document Updates
| 4. Issue Log (Action Item Log) (Each Issues should be assigned to one Owner) | 3. Management Skills | 4. Organizational Process Assets Upd
5. Change Log
6. Organizational Process Assets
RISK
PROCUREMENT
Conduct Procurements:
EXECUTING | 1. Project Management Plan (Pr M Pl) | 1. Advertising | 1. Selected Sellers
| 2. Project Documents | 2. Internet Search | 2. Procurement Contract Award
| 4. Procurement Documents | 3. Bidder Conference | 3. Resource Calendars
| 3. Teaming Agreements | 4. Proposal Evaluation Techniques | 4. Change Requests
| 5. Make-or-Buy Decisions | 5. Independent Estimates ('Should-Cost' Estimate) | 5. Project Management Plan Updates
| 6. Source Selection Criteria | 6. Procurement Negotiations | 6. Project Document Updates
| 7. Qualified Sellers' List | 7. Expert Judgement
8. Seller Proposal
9. Organizational Process Assets

## M&C
INTEGRATION
Sl# | Inputs | Tools & Techniques | Outputs
4 | Monitor and Control Project Work:
M & C | 1. Project Management Plan | 1. Expert Judgment | 1. Change Requests
| 2. Performance Reports |  | 2. Project Management Plan Updates
| 3. Enterprise Environmental Factors |  | 3. Project Document Updates
4. Organizational Process Assets
5 | Perform Integrated Change Control:
M & C | 1. Project Management Plan | 1. Expert Judgment | 1. Change Request Status Updates
| 2. Work Performance Information | 2. Change Control Meetings | 2. Project Management Plan Updates
| 3. Change Requests |  | 3. Project Document Updates
4. Enterprise Environmental Factors
5. Organizational Process Assets
SCOPE
10 | Verify Scope:
M & C | 1. Project Management Plan | 1. Inspection | 1. Accepted deliverables
| 2. Requirements Documentation | (It involves a point-by-point review of the Scope and the associated Deliverable). Examine the deliverables, Measure it, Inspect it, and Weigh it. | 2. Change Requests
| 3. Requirements Traceability Matrix |  | 3. Project Document Updates
4. Validated Deliverables
11 | Control Scope:
M & C | 1. Project Management Plan | 1. Variance analysis | 1. Work Performance Measurements
| 2. Work Performance Information | VA can be used to measure differences btwn what was defined in the Scope Baseline & what was created. It is useful in this process as a way to investigate and understand the root causes behind these differences. | 2. Change Requests
| 3. Requirements Documentation |  | 3. Project Management Plan Updates
| 4. Requirements Traceability Matrix |  | 4. Project Document Updates
| 5. Organizational Process Assets |  | 5. Organizational Process Assets Updates
TIME
17 | Control Schedule:
M & C | 1. Project Management Plan | 1. Performance Reviews | 1. Work Performance Measurements (SV & SPI values)
| 2. Project Schedule | 2. Variance Analysis (SV/SPI) | 2. Change Requests
| 3. Work Performance Information | 3. Resource Leveling | 3. Project Management Plan Updates
| 4. Organizational Process Assets | 4. What-if Scenario Analysis | 4. Project Document Updates
|  | 5. Adjusting Leads and Lags | 5. Organizational Process Assets Updates
6. Schedule Compression
7. Scheduling Tool
8. Project Management Software
COST
20 | Control Costs:
M & C | 1. Project Management Plan | 1. Earned Value Management (Variances and Trends) | 1. Work Performance Measurements
| 2. Project Funding Requirements | 2. Forecasting (EAC and ETC) | 2. Budget Forecasts
| 3. Work Performance Information | 3. To-complete Performance Index (TCPI) | 3. Change Requests
| 4. Organizational Process Assets | 4. Performance Reviews | 4. Project Management Plan Updates
|  | 5. Variance Analysis | 5. Organizational Process Assets Upd
|  | 6. Project Management Software | 6. Project Document Updates
QUALITY
23 | Perform Quality Control:
MONITORING & CONTROLLING | 1. Project Management Plan (Q M Plan) | 1. Cause and Effect Diagram (Ishikawa/Fishbone) | 1. Quality Control Measurements
| 2. Quality Metrics | 2. Control Charts | 2. Validated Changes
| 3. Quality Checklists | 3. Flowcharting | 3. Validate Deliverables
| 4. Deliverables | 4. Histogram | 4. Change Requests
| 5. Approved Change Requests | 5. Pareto Chart | 5. Project Management Plan Updates
| 6. Work Performance Measurements | 6. Run Chart | 6. Project Document Updates
| 7. Organizational Process Assets | 7. Scatter Diagram | 7. Organizational Process Assets Updates
8. Statistical Sampling
9. Inspection
10. Approved Change Requests Review
HUMAN RESOURCE
COMMUNICATIONS
32 | Report Performance:
M & C | 1. Project Management Plan (Performance Measurement Baseline - It includes Cost, Schedule, Scope, Tech, and Other Baselines) | 1. Variance Analysis - Backward Looking Tool (It is an after-the-fact) | 1. Performance reports (It shows how the project is progressing against the various baselines (Scope, Time, Cost and Quality).
| 2. Work Performance Information (Deliverables Status, Schedule Progress, and Costs Incurred) | 2. Forecasting Methods - Forward Looking Tool (EAC, ETC) | Common Formats - Bar Charts, S-curves, Histograms, and Tables. Variance, EV, Forecasting.
| 3. Work Performance Measurements (CV, SV, CPI, CPIc, SPI) | 3. Communication Methods (PM generally uses a PUSH Comm Technique) | 2. Change Requests
| 4. Budget Forecasts | 4. Reporting Systems (Standard Tool for PM to Capture, | 3. Organizational Process Assets Updates
| 5. Organizational Process Assets | Store and Distribute Information)
RISK
38 | Monitor and Control Risks:
M & C | 1. Risk Register | 1. Risk Audits | 1. Risk Register Updates
| 2. Project Management Plan | 2. Reserve Analysis | 2. Change Requests
| 3. Performance Reports | 3. Risk Reassessment | 3. Project Management Plan Updates
| 4. Work Performance Information | 4. Status Meetings | 4. Project Document Updates
| No O.P.A & E.E.F | 5. Technical Performance Measurement | 5. Organizational Process Assets Updates
6. Variance and Trend Analysis
PROCUREMENT
41 | Administer Procurements:
M & C | 1. Project Management Plan | 1. Inspections and Audits | 1. Procurement Documentation
| 2. Procurement Documents | 2. Procurement Performance Reviews | 2. Change Requests
| 3. Contract | 3. Performance Reporting | 3. Project Management Plan Updates
| 4. Approved Change Requests | 4. Contract Change Control System | 4. Organizational Process Assets Updates
| 5. Performance Reports | 5. Payment System
| 6. Work Performance Information | 6. Claims Administration
7. Records Management System